## SIT 2 testing workbook
Shopify Consumer E-Commerce
[6 empty] | Bio true | [5 empty] | Lumify
Test Case # | Section | Scenario | Test Case | Test Steps | Expected results | Actual result | Pass / Fail | Test Date | Tester Comment | Developer Comment | Status | Actual result | Pass / Fail | Test Date | Tester Comment | Developer Comment | Status
1 | Static Pages | Home Page(header, mast and collection) | Header check | Top line colour should be as per the brand guidelines | Home page top line colour should be dark blue. | Same as expected | Pass
2 |  |  |  | All Logo Placement should be as per the guidelines. | All home page logo should placed on the top left | Same as expected | Pass
3 |  |  |  | Product Dropdown should be visible with all product list. | Product dropdown should be visible with all related brand products. Marketplace should have all brands listed in the dropdown | Same as expected | Pass
4 |  |  |  | The link to Login should work fine user should redirect to login page. | After click on login button user should redirect to login page. | Same as expected | Pass
5 |  |  |  | The link to Cart should work fine user should redirect to my cart page. | After click on cart button user should redirect to my cart page. | Same as expected | Pass
6 |  |  |  | Cart: Num of items | Number of items should be shown next to the cart icon | Same as expected | Pass
7 |  |  | Marketing Banner (mast) check | Num of items in a banner | All Marketing mast images should be visible on home page | Same as expected | Pass
8 |  |  |  | Working of carousel | Crousel navigation should work when the user presses the left and right buttons | Not available | Fail
9 |  |  | Product Collections Check | Disclaimer available at the top of the collections | Disclaimer "*These statements have not been evaluated by the Food and Drug Administration. These products are not intended to diagnose, treat, cure or prevent any disease." available at the top of the collections | Not available | Fail
10 |  |  |  | Check Product list | 3 products should be visible | Same as expected | Pass
11 |  |  |  | Product individual check. | Clicking on any link on particular product, the user should be able to view selected product details on the Products page | Same as expected | Pass
12 |  |  |  | Product One Time Price Check | Product one time pricing shown in collections should be correct | Same as expected | Pass
13 |  |  |  | Product Subscription Price Check | Product subscription pricing shown in collections should be correct | Not available | Fail |  | Showing coming soon
14 |  | Browse to all Footer pages | Check "Learn" link | Check "Privacy Policy" link | After click on "Privacy Policy" link new pop up should come on the page. | Same as expected | Pass
15 |  |  |  | Check Pop up window | "Just A Moment... This link takes you to another site at www.bauschhealth.com. Do you want to proceed? | Same as expected | Pass
16 |  |  |  | Check "Cancel" button | After click on "Cancel" button user should go back to his current page. | Same as expected | Pass
17 |  |  |  | Check cross sign | After click on cross sign pop up should close | Same as expected | Pass
18 |  |  |  | Check "Take Me There" button | After click on "Take Me there" button user should redirect to "Privacy Policy" page. | Same as expected | Pass
19 |  |  |  | The link to Refund Policy should work fine | User should able to redirect refund policy page. | Same as expected | Pass
20 |  |  |  | The link to Customer Care should work fine | User should able to redirect customer care page. | Same as expected | Pass
21 |  |  |  | The link to Subscriptions FAQ should work fine | User should able to redirect subscriptions faq page. | Same as expected | Pass
22 |  |  |  | The link to Contact Us should work fine | User should able to redirect contact us page. | Same as expected | Pass
23 |  |  |  | The link to Legal Notice should work fine | User should able to redirect legal notice page. | Same as expected | Pass
24 |  |  | Contact Us | Check "Contact Us" link should available | User should be able to click on "Contact Us" link. | Same as expected | Pass
25 |  |  |  | After click on "Contact Us" link user should redirect to "Contact Us" page. | User should be able to see all "Contact Us" page description. | Same as expected | Pass
26 |  |  |  | Brand "Contact number" and "email_id" should be visible | User should be able to see company "Contact Details". | Same as expected | Pass
27 |  |  |  | "Hours of Operation: Monday thru Friday 8:00 am to 8:00 pm EST" User should see this details on "Contact Us" page | User should see this details. | Same as expected | Pass
28 |  |  |  | "Name" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as expected | Pass
29 |  |  |  | "Email" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as expected | Pass
30 |  |  |  | After providing wrong email it should show error message "Email is invalid" | Email field should not accept wrong email it should show error message. | Same as expected | Pass
31 |  |  |  | Blank "Email" field should not accept | User should not able blank to provide blank "Email" field. | Same as expected | Pass
32 |  |  |  | "Phone Number" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as expected | Pass
33 |  |  |  | "Message" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as expected | Pass
34 |  |  |  | Blank "Message" field should not accept | User should not able to provide blank "Message" field it show error message " Please fill out this field" | Same as expected | Pass
35 |  |  |  | Check after click on "Privacy Policy" link user should redirect to "PRIVACY POLICY" page. | User should redirect to "https://www.bauschhealth.com/privacy" | Same as expected | Pass
36 |  |  |  | Check after click on "Legal Notice" link user should redirect to "LEGAL NOTICE" page. | User should redirect to "https://www.bauschhealth.com/terms" | Same as expected | Pass
37 |  |  |  | Check "Submit" button | "Submit" button should be visible with the colour as per the brand guideline | Not available | Fail |  | Contact button is available
38 |  |  |  | User should be able to click on "Submit" button. | After click on "Submit" button it should show "Thanks for contacting us. We'll get back to you as soon as possible" | Message is different it show "We have received your message and will get back to you shortly. Thank you!" | Fail
39 |  |  |  | After providing all "Contact Us" page details "Submit button" should work. | User need to provide all "Contact Us" page detail before click on "Submit" button. | Same as expected | Pass
40 |  |  | Check "Shop" links | The link to AREDS 2 Soft Gels should work fine | User should able to redirect areds 2 soft gels page. | Same as expected | Pass
41 |  |  |  | The link to AREDS 2 Chewables should work fine | User should able to redirect areds 2 Chewables page. | Same as expected | Pass
42 |  |  |  | The link to AREDS2 + Multivitamin should work fine | User should able to redirect areds2 + multivitamin page. | Same as expected | Pass
43 |  |  | Check "Account" link | The link to Log In should work fine | User should able to redirect log in page. | Same as expected | Pass
44 |  |  |  | The link to Register should work fine | User should able to redirect register page. | Same as expected | Pass
45 |  |  |  |  | User should able to redirect do not sell my personal information page. | Same as expected | Pass
46 |  |  | Check all Footer details. | Footer line colour | Footer line colour should be as per brand guidelines | Same as expected | Pass
47 |  |  |  | Footer disclaimer check | Footer disclaimer should be visible and correct | Same as expected | Pass
48 |  |  |  | Check California residents link. The link to Do not sell my personal information should work fine | After click on link user should be able to redirect to "California residents" page | Same as expected | Pass
49 |  |  |  | Payment getway logo | All payment logo should be visible in footer page. | Same as expected | Pass
50 |  | Unsubscribe Bar check | Check all opt-outs | Unsubscribe | User should be directed to https://cloud.marketing.bausch.com/Privacy-Page-Unsubscribe | Same as expected | Pass
51 |  |  |  | Do Not Sell or Share My Personal Information | User should be directed to https://cloud.marketing.bausch.com/do-not-sell-or-share | Same as expected | Pass
52 |  |  |  | Do Not Target | User should be directed to https://cloud.marketing.bausch.com/do-not-target | Same as expected | Pass
53 |  |  |  | Limit the Use of My Sensitive Personal Information | User should be directed to https://cloud.marketing.bausch.com/Limit-Sensitive-Personal-Information-Usage | Same as expected | Pass
54 | Login | User Login (positive + negative) | Check "Sign In" button | User should be logged into the account after providing correct email and password. | After click on sign in button with correct email & password user should be able to login. | Same as expected | Pass
55 |  |  |  | By providing wrong email user should not be able to log-in. It should show error message (Incorrect email or password). | User should not be logged after entered wrong email id | Same as expected | Pass
56 |  |  |  | By providing wrong password user should not be able to log-in. It should show error message (Incorrect email or password). | User should not be logged after entered wrong password | Same as expected | Pass
57 |  |  |  | Colour of "Sign In" button colour should be as per the brand guidelines | Sign In button colour should be as per the brand guidelines | Same as expected | Pass
58 |  |  |  | After click on "sign In" button with correct credentials user should redirect "My Account" page. | User should be able to see "My Account" page details. | Same as expected | Pass
59 |  | Forgot Password (positive + negative) | Check Forgot your password button | Login page "Forgot Your Password" link should be available next to the "Sign In" button | After click on forgot your password user should be able to redirect forgot password page. | Same as expected | Pass
60 |  |  |  | User should be able to enter register email & after click on "Recover Password" user should received reset your password link on his register email | Forgot password link should received on user register email | Link is received on register mail id but link is not working | Fail
61 |  |  |  | Cancel link should be available on Forget your password page. | After click on Cancel link user should able to back to login page. | Same as expected | Pass
62 |  |  |  | Provided email address should be pre-registered | Provided email address should be registered otherwise show error message "No account found with that email" | It accept not registered mail id and It show different message "If you are registered with our store, we will send a reset password to your email address." | Fail
63 |  |  |  | Provided email address should be in correct format | Provided email address should be in correct format otherwise show error message "No account found with that email" | Same as expected | Pass
64 |  | User Registration (positive + negative) | Check Register button | Click on register button user should be redirect to Create account page. | User should able redirect to Create account page. | If providing already registered mail id not showing any error message. | Fail |  | Below error message is visible in existing site "This email address is already associated with an account. If this account is yours, you can reset your password"
65 |  |  | Check Create button | User should be able to enter first name, last name, email and password. | User should able to fill all create account page details. | Same as expected | Pass
66 |  |  |  | Successful user account creation | After providing correct user details, user account should be created. | Same as expected | Pass
67 |  |  |  | First Name should not be blank | Provide blank First Name | Same as expected | Pass
68 |  |  |  | Last Name should not be blank | Provide blank Last Name | Same as expected | Pass
69 |  |  |  | Email Address should not be blank | Provide blank Email Address | Same as expected | Pass
70 |  |  |  | Passwords must be a minimum of 5 characters long and special characters are allowed. | Password field only accept more than 5 characters and special characters. | Same as expected | Pass
71 |  |  |  | Password field not accept 4 character password it should show error message (Password is too short (minimum is 5 characters). | Password field not accept 4 character password it should show error message. | Same as expected | Pass
72 |  | My Account Page | Logout | Check "Logout" link user should be able to logout. | After click on "Logout" link user should be logout. | Same as expected | Pass
73 |  |  |  |  | User to be redirected to the Homepage (Marketplace) | Same as expected | Pass
74 |  |  | User Details | Name should be as per what was submitted at the time of the user creation | User should see submitted user name | Same as expected | Pass
75 |  |  |  | Email Address should be as per what was submitted at the time of the user creation | User should see submitted Email address | Same as expected | Pass
76 |  |  |  | Default Address should be as per what was submitted at the time of the user creation | User should see submitted default address | Same as expected | Pass
77 |  |  | Subscriptions | Go to "Manage your Subscriptions" | Click on the link "Manage your Subscriptions" to go to the Subscription page | After click on link showing error message "This is our 404" | Fail
78 |  |  |  | Go to "Having issues managing your subscriptions?" | Click on the link "Having issues managing your subscriptions?" to go to Get Subscription Access page | After click on link showing error message "This is our 404" | Fail
79 |  |  | Get Subscription Access | Submit email id to register as a Subscription user | User to get email notification stating that they have access to the Subscriptions now | After click on link showing error message "This is our 404" | Fail
80 |  |  |  |  | Registered user should be able to go to the "Manage your Subscriptions" page | After click on link showing error message "This is our 404" | Fail
81 |  |  | Manage your Subscriptions | View Subscription list | User should be able to see all of their Past and Active Subscriptions in a list when thy land on "Manage your Subscription" page | After click on link showing error message "This is our 404" | Fail
82 |  |  |  | View individual Subscription | On clicking any Past or Active Subscription, user should be able to see the individual Subscription showing Product, Price, Frequency details and Selected Delivery Address as selected at the time of initiating the Subscription | After click on link showing error message "This is our 404" | Fail
83 |  |  |  | Edit Subscription - Quantity | User should have the ability to change the quantity of the Product in their Subscription | After click on link showing error message "This is our 404" | Fail
84 |  |  |  | Edit Subscription - Frequency | User should have the ability to change the Frequency of delivery in their Subscription | After click on link showing error message "This is our 404" | Fail
85 |  |  |  | Edit Subscription - Change Delivery Address | User should have the ability to change the Delivery Address in their Subscription | After click on link showing error message "This is our 404" | Fail
86 |  |  |  | Delete Subscription | User should have the ability to cancel the Active subscription | After click on link showing error message "This is our 404" | Fail
87 |  |  | View Default Address | Present Default Address should be visible in this section as the "Default Address" | User Default Address should be visible under "Default Address" heading on the Account page | Same as expected | Pass
88 |  |  |  | Check View Address link | After click on "View Addresses" link user should redirect to My addresses page. | Link is not available | Fail
89 |  |  | Manage Address | Go to My Account | After click on "My Account" link user should see all user submitted details. | Manage Address link not working | Fail
90 |  |  |  | View Address | User should be able to view all previously entered address under the "Addresses" section of the page | Manage Address link not working | Fail
91 |  |  |  |  | Under the "Addresses" section of the page, there should be one address marked as "default Address" | Manage Address link not working | Fail
92 |  |  |  |  | Under each on the listed address there should be a link to "Edit" and "Delete" the address | Manage Address link not working | Fail
93 |  |  |  | Add New Address | All address fields should accept alphanumeric and special character. | Manage Address link not working | Fail
94 |  |  |  |  | User should be able click "Country/region" drop down and select "United States" | Manage Address link not working | Fail
95 |  |  |  |  | "First name" field should accept alphanumeric and special character. | Manage Address link not working | Fail
96 |  |  |  |  | "Last name" field should accept alphanumeric and special character . | Manage Address link not working | Fail
97 |  |  |  |  | "Company" field should accept alphanumeric and special character . | Manage Address link not working | Fail
98 |  |  |  |  | "Address" field should accept alphanumeric and special character . | Manage Address link not working | Fail
99 |  |  |  |  | "Apartment, suite, etc." field should accept alphanumeric and special character . | Manage Address link not working | Fail
100 |  |  |  |  | "City" field should accept alphanumeric and special character . | Manage Address link not working | Fail
101 |  |  |  |  | "State" drop down should be work all state list should be visible in the drop down and user should be able to select specific state. | Manage Address link not working | Fail
102 |  |  |  |  | "ZIP code" field should accept alphanumeric and special character . | Manage Address link not working | Fail
103 |  |  |  |  | "Phone" field should accept only numeric values. | Manage Address link not working | Fail
104 |  |  |  |  | "Phone" field should not accept character and special character values it show error message "Please match the requested format" | Manage Address link not working | Fail
105 |  |  |  | Set Default Address | User should be able Check and unchecked "Set default" checkbox | Manage Address link not working | Fail
106 |  |  |  |  | After click on "Add Address" button Address should be add with all the provided details. | Manage Address link not working | Fail
107 |  |  |  | Edit Address | After click on Edit link user should be redirect to "Edit address" page. | Manage Address link not working | Fail
108 |  |  |  |  | User should be able click "Country/region" drop down and select "United States" | Manage Address link not working | Fail
109 |  |  |  |  | "First name" field should accept alphanumeric and special character. | Manage Address link not working | Fail
110 |  |  |  |  | "Last name" field should accept alphanumeric and special character . | Manage Address link not working | Fail
111 |  |  |  |  | "Company" field should accept alphanumeric and special character . | Manage Address link not working | Fail
112 |  |  |  |  | "Address" field should accept alphanumeric and special character . | Manage Address link not working | Fail
113 |  |  |  |  | "Apartment, suite, etc." field should accept alphanumeric and special character . | Manage Address link not working | Fail
114 |  |  |  |  | "City" field should accept alphanumeric and special character . | Manage Address link not working | Fail
115 |  |  |  |  | "State" drop down should be work all state list should be visible in the drop down and user should be able to select specific state. | Manage Address link not working | Fail
116 |  |  |  |  | "ZIP code" field should accept alphanumeric and special character . | Manage Address link not working | Fail
117 |  |  |  |  | "Phone" field should accept only numeric values. | Manage Address link not working | Fail
118 |  |  |  |  | "Phone" field should not accept character and special character values it show error message "Please match the requested format" | Manage Address link not working | Fail
119 |  |  |  |  | User should be able Check and unchecked "Set default" checkbox | Manage Address link not working | Fail
120 |  |  |  |  | After click on "Update Address" button edited address field's should be updated. | Manage Address link not working | Fail
121 |  |  |  |  | After click on "Cancel" link user should be back to "Add New Address "page. | Manage Address link not working | Fail
122 |  |  |  | Delete Address | User should be able to delete existing address. | Manage Address link not working | Fail
123 |  |  |  |  | User should be able to delete all of their listed address | Manage Address link not working | Fail
124 |  |  | Order History | Order history (for Single time buy and Subscription) should be visible on "My Account" page. | User should be able to see "Order History". | Same as expected | Pass
125 |  |  |  | User should be able to see the individual Order Details | On click on the individual Order, user should be shown the Order Details, which should contain information regarding Product, Price, Qty, Amount Paid, Date of Order and Order Status | Does not land on order details page | Fail |  | Redirects to login page though already logged in
126 |  |  |  | If user haven't placed any order it should show a standard message | User should see "You haven't placed any orders yet." | Same as expected | Pass
127 |  |  | Request for Replacement Order | From the individual Order Details page, user should be able to order for a Replacement as per the defined terms | Click on "TO BE FILLED" to order the replacement Product | Not working | Fail
128 | Product | Product Scenario | Check Product Page all elements | Product image zoom in and zoom out and scroll left and right side should work fine | Product images user should able to see with zoom and scroll left and right side. | Not working | Fail
129 |  |  |  | Product name should be visible as per brand guideline colour and font. | User should see selected product name. | Not visible | Fail
130 |  |  |  | User Rating stars should be visible | User should see product rating. | Not visible | Fail
131 |  |  |  | Total Number of review's written should be visible as a number next to the star ratings | User should see number of total review's written for the product | Not visible | Fail
132 |  |  |  | After click on "star rating" or "reviews" link user should go to "Customer Reviews" page. | User should redirect to "Customer Reviews" page. | Not available | Fail
133 |  |  |  | Product price(s) should be visible in dollar | User should be able to see product price in dollar. | Same as expected | Pass
134 |  |  |  | "One Time Purchase" check box should be available .if One Time plan is activated for the Product | User should be able to check "One Time Purchase" | Same as expected | Pass
135 |  |  |  | User should be able to check only one check box at one time . | User should able to check only one box at one time either "Subscribe to save" or "one time purchase checkbox". | Same as expected | Pass
136 |  |  |  | "Subscribe to Save" check box should be available if Subscription plan is activated for the Product | User should be able to check ""Subscribe to Save" | Showing coming soon price is not visible | Fail
137 |  |  |  | After checking "Subscribe to Save" checkbox price will be change to a discounted price | User should be able to see price difference after checked "Subscribe to Save" checkbox. | Same as expected | Pass
138 |  |  |  | After cheking "Subscribe to Save" check box "Delivery every" drop down should be visible | User should be able to select specific "Deliver Every" frequency. | Same as expected | Pass
139 |  |  |  | Days mentioned in the delivery frequency dropdown for a subscription, should be as per what is mentioned in Recharge for the product with a recommended option | Delivery frequency and Days recommended should match with Recharge values | Not visible | Fail
140 |  |  |  | After clicking on "Subscribe to Save" - "Save more on your subscription order with your Sight Matters coupon code." this tag line should be visible as per brand guideline colour and font. | User should be able to see "Save more on your subscription order with your Sight Matters coupon code." | Not available | Fail
141 |  |  |  | Check "Subscription Details" link should available | User should be able to click on "Subscription Details" link. | "Learn link" available but not in different colour it's not user friendly. | Fail
142 |  |  |  | After clicking on "Subscription Details" link new pop up should come with a tagline "Products are automatically delivered on the schedule you choose" and "Learn More" link. | User should be able to click on "Learn More" link. | Reditrect to "Subscriptions" FAQ page | Fail
143 |  |  |  | After clicking on "Learn More" link user should redirect to "Customer Care" page. | User should redirect to "Customer Care" page and see all details. | Same as expected | Pass
144 |  |  | Product Quantity Check | Product quantity select (+) and (-) button should be available and working | User should be able to add and remove product quantity before adding in the cart. | Same as expected | Pass
145 |  |  |  | By clicking on (+) button, value of Qty should increment by 1 | After click on (+) button product quantity should increased by 1. | Same as expected | Pass
146 |  |  |  | By clicking on (-) button, value of Qty should decrement by 1 | After click on (-) button product quantity should decreased by 1. | Same as expected | Pass
147 |  |  |  | Value of Qty should not go above 99 | User should not able to add product quantity more than 99 | Same as expected | Pass
148 |  |  |  | Value of Qty should not go below 0 | User should not able to select product quantity less than 1 | Same as expected | Pass
149 |  |  |  | Check "Add to Cart" button | Add to cart button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
150 |  |  |  | After click on " Add to Cart" button "Added to cart" this tagline and "View cart and check out." link come on top of the page with brand guideline colour. | User should see top of the page new tag line after click on "Add to Cart" button. | Same as expected | Pass
151 |  |  | Product Inventory Check | Value of Qty should not go above the available inventory quantity for the product | User should not able to add quantity more than available inventory quantity. | Same as expected | Pass
152 |  |  |  | If there is no inventory for the Product, the "Add to Cart" button label should get changed to "Temporarily Unavailable" | If product in not available it should show "Temporarily Unavailable". | Same as expected | Pass
153 |  |  | Product Marketing Information Section | Product Marketing section should be displayed if Marketing banner is provided by the Products/Marketing team | User should be able to see product marketing banner if product team provided. | Same as expected | Pass
154 |  |  |  | Product Marketing section should not be displayed if Marketing banner is not provided by the Products/Marketing team | User should not be able to see product marketing banner if product team not provided. | Only visible for preservision products | Fail
155 |  |  |  | Disclaimer available at the bottom of the Product Marketing Section | Disclaimer "*These statements have not been evaluated by the Food and Drug Administration. These products are not intended to diagnose, treat, cure or prevent any disease." available at the below of the Ingredient matter | Same as expected | Pass
156 |  |  | Shop Our Other Products | "Shop our other product" should be visible on all product pages | User should be able to see other products. | Same as expected | Pass
157 |  |  |  | User should see brand other product image, product link, product one time purchase price and subscription price. | User should see brand other product details. | Same as expected | Pass
158 |  |  |  | After click on individual product image user should see new pop up with product detail's, product images. | User should see product detail's. | Same as expected | Pass
159 |  |  | Check Customer review (submission only) | "Customer Reviews" header should be visible as per brand guideline colour and font. | User should see "Customer Reviews" header. | Reviews not available | Fail
160 |  |  |  | Check Disclaimer | User should see disclaimer. | Reviews not available | Fail
161 |  |  |  | After click on "Please review the Full Product Reviews Disclaimer" all disclaimer should be visible. | User should be able to see all disclaimer. | Reviews not available | Fail
162 |  |  |  | "Star" rating should be visible with mentioned "Based on quantity reviews" | User should see product rating. | Same as expected | Pass
163 |  |  |  | After click on "write a review" link user should be able to see "Write a review" page | User should be able to see "Write a review" page. | Same as expected | Pass
164 |  |  |  | Check "Name" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Name" field. | Same as expected | Pass
165 |  |  |  | Check blank "Name" field should not accept. | User can't submit a review with blank "Name" | Same as expected | Pass
166 |  |  |  | Check "Email" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Email" field. | Same as expected | Pass
167 |  |  |  | Check blank "Email" field should not accept. | User can't submit a review with blank "Email" | Same as expected | Pass
168 |  |  |  | "Email" field accept only email | "Email" field should not accept without "@" | Same as expected | Pass
169 |  |  |  | Check "Rating" | User should be able to select "Star" rating | Not available | Fail
170 |  |  |  | Check blank "Rating" field should not accept. | User can't submit a review with blank "Rating" | Same as expected | Pass
171 |  |  |  | Check "Review Title" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Review Title" field. | Same as expected | Pass
172 |  |  |  | Check blank "Review Title" field should not accept. | User can't submit a review with blank "Review Title" | Same as expected | Pass
173 |  |  |  | Check "Body of Review (1500)" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Body of Review (1500)" field. | Same as expected | Pass
174 |  |  |  | Check blank "Body of Review (1500)" field should not accept. | User can't submit a review with blank "Body of Review (1500)" | Same as expected | Pass
175 |  |  |  | Check "Body of Review (1500)" field should not accept more 1500 characters. | User should not be able to enter more than 1500 character. | Takes more than 1500 characters | Fail
176 |  |  |  | Check "Body of Review (1500)" accept minimum '3' character | User need to be enter minimum '3' character "Body of Review (1500)" | Showing different error message | Fail |  | Please fill out this field
177 |  |  |  | Write a review field's should not accept blank it should show error message. | It should show error message "Not all the fields have been filled out correctly!" | Same as expected | Pass
178 |  |  |  | Check "Submit Review" button should be work | Submit review button should be visible with colour as per brand guidelines. | Same as expected | Pass
179 |  |  |  | After click on "Submit Review" button customer should be able to submit a customer review | After entered all Customer review field's user should be able to submit his review clicking on "Submit Review" button. | Not visible any message after submit review | Fail
180 |  |  |  | After successfully submit a review user should see "Thank you for submitting a review!" line. | User should see "Thank you for submitting a review!" line. | Redirect to product page | Fail
181 |  |  |  | Other user's review should be visible | Customer should be able to read other customer review's. | Same as expected | Pass
182 |  |  |  | Other user submitted rating star should be visible. | User should be able see "Star" rating. | Same as expected | Pass
183 |  |  |  | Other user review header should be visible with colour and font should be as per brand guideline. | User should be able to read review header | Same as expected | Pass
184 |  |  |  | Review submitted user name and review published date should be visible. | User should be able to read review submitted customer name and published date. | Same as expected | Pass
185 |  |  |  | Review description should be visible. | User should be read review description. | Not working | Fail
186 |  |  |  | Check "Report as Inappropriate" link should be work | After click on "Report as Inappropriate" new pop-up should come its should ask "Are you sure you want to report this review as inappropriate?" with "Ok" and "Cancel" button. | Not working | Fail
187 |  |  |  | Anyone can mark an already published review as "Report as Inappropriate" | Customer should be able to mark review as "Report as Inappropriate". | Not working | Fail
188 |  |  |  | Any review that is marked as "Inappropriate", should generate an alert at the backend for moderation | After customer submit "Report as Inappropriate" review it should be generate an alert at the backend for moderation. | Not working | Fail
189 |  | Check Single buy | Check "One Time Purchase" Buy | Check "One Time Purchase" checkbox | User should be able to check "One Time Purchase" checkbox. | Same as expected | Pass
190 |  |  |  | After click on "Add to Cart" button "My Cart" window should come on right side. | User should be able to see "My Cart" page details after click on "Add to Cart" button. | Same as expected | Pass
191 |  |  | Check "My Cart" drawer | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass
192 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Same as expected | Pass
193 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass
194 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
195 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via Recharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via Recharge") | Same as expected | Pass
196 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
197 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
198 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Same as expected | Pass
199 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity and Subtotal | User should see all added products in the cart with details. | Same as expected | Pass
200 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass
201 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Same as expected | Pass
202 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass
203 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | Not visible | Fail
204 |  |  |  | Product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Not available | Fail
205 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
206 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping, taxes, and discounts codes are calculated at checkout." | User should see tagline "Shipping, taxes, and discounts codes are calculated at checkout." | Same as expected | Pass
207 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass
208 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass
209 |  |  |  | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass
210 |  |  |  | After click on "Checkout" button user should redirect to "Contact information & Shipping address" page | User should redirect to "Contact & Shipping address" page | Not visible | Fail
211 |  |  | Contact information | Check "Contact information" details | User should see his registered name and email | Blank fields availble | Fail
212 |  |  |  | Check "Log out" link | After click on "Log out" link user account should log out | Not available | Fail
213 |  |  |  | Check box | User should be able to check on " Yes, I would like to receive promotional communications from Bausch + Lomb." checkbox. | Same as expected | Pass
214 |  |  |  | Below the check box user should see disclaimer | By submitting your information you confirm you have read and agree with the terms of our Privacy Policy and Legal Notice . | Not available | Fail
215 |  |  |  | The link to privacy Policy should work fine | User should able to redirect to privacy policy page. | Same as expected | Pass
216 |  |  |  | The link to Legal Notice should work fine | User should able to redirect legal notice page. | Same as expected | Pass
217 |  |  | Order Summary | Selected product should be the same as selected by customer while making the order | Order list should be comparable to what was present in the respective Cart (use Cart ID) | Same as expected | Pass
218 |  |  |  | Product image, product name and product price should be visible. | User should see product details. | Same as expected | Pass
219 |  |  |  | Check Discount code | User should be able to enter discount code in the field. | Same as expected | Pass
220 |  |  |  | After enter "Discount - code " click on "Apply" button. | After click on "Apply" button "Discount - code " should applied. | Not available | Fail
221 |  |  |  | User should see Subtotal, Shipping, Estimated taxes and Total . | User should be able to see product price calculated values. | Estimated taxes | Fail
222 |  |  |  | Check "Estimated taxes" | Estimated taxes should be calculated 7.5% of the product price. | Same as expected | Pass
223 |  |  |  | Check "Total" | "Total" should be addition of Subtotal, Shipping and Estimated taxes | Not available | Fail
224 |  |  | Shipping Address | Check "Shipping Address" field's. | User should see his already saved address on "Shipping Address" field's. | Same as expected | Pass
225 |  |  |  | Check "Saved Addresses" drop down. | User should see all saved address list in the drop down and able to select any one address in list. | Same as expected | Pass
226 |  |  |  | Check "Country/region" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country/region" drop down. | Same as expected | Pass
227 |  |  |  | Check "First name" field | User should see saved his "First name" and able to edit. | Same as expected | Pass
228 |  |  |  | Check "Last name" field | User should see saved his "Last name" and able to edit. | Same as expected | Pass
229 |  |  |  | Check "Address" field | User should see saved his "Address" and able to edit. | Same as expected | Pass
230 |  |  |  | Check "Apt, suite, etc." field | User should see saved his "Apt, suite, etc." and able to edit. | Same as expected | Pass
231 |  |  |  | Check "City" field | User should see saved his "City" and able to edit. | Same as expected | Pass
232 |  |  |  | Check "State" field | User should see selected his "Last name" and able to select another state in the drop down.. | Not available | Fail
233 |  |  |  | Check "Zip code" field | User should see saved his "Zip code" and able to edit. | Same as expected | Pass
234 |  |  |  | Check "Return to Cart" link | After click on "Return to cart" link user should redirect "Shopping Cart" page. | Same as expected | Pass
235 |  |  |  | Check "Continue" button | Check "Continue" button should be work with colour as per brand guidelines. | Same as expected | Pass
236 |  |  | Payment page | After click on "Continue" button user should redirect "Payment" page. | User should redirect to another page. | Same as expected | Pass
237 |  |  |  | Check "Contact" | Email_id should be visible and after click on "change" link user should redirect back to shipping page | Economy and standard checkbox available | Fail
238 |  |  |  | Check "Ship to" | Shipping details should be visible and after click on "change" link user should redirect back to shipping page | Same as expected | Pass
239 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Same as expected | Pass
240 |  |  |  | Check "Return to information" link | After click on "Return to information" user should redirect to shipping page. | Same as expected | Pass
241 |  |  |  | Check "Continue to payment" button | Check "Continue to payment" button should be work with colour as per brand guidelines. | Economy and standard method available | Fail |  | Free not available
242 |  |  |  |  | After click on "Continue to payment" button user should redirect "Payment" page. | Same as expected | Pass
243 |  |  |  | Check "Method" | It should show "Free Standard Shipping · Free" | Same as expected | Pass
244 |  |  |  | Check disclaimer | Payment- "All transactions are secure and encrypted." | Same as expected | Pass
245 |  |  |  | Check "Credit Card" field's. | User should see card logo. | Same as expected | Pass
246 |  |  |  | Check "Card number" field should accept only numeric values | User should be able to enter only numeric values in "Card number" field. | Card number is not visible as per format | Fail |  | It accept 16 digit but format not same as per existing site.
247 |  |  |  | Check "Card number" field should not accept character values. | User should not able to enter character values in "Card number" field. | Same as expected | Pass
248 |  |  |  | Check "Card number" field length should accept only 16 numeric values | User should be able to enter "Card number" length accept only 16 numeric values | Same as expected | Pass
249 |  |  |  | Blank "Card number" field should not accept it should show error massage (Your card number is incomplete.) | "Card number" field should not accept blank | Same as expected | Pass
250 |  |  |  | Check "Name on card "should accept character and numeric values | "Name on card" field should accept character and numeric values. | Same as expected | Pass
251 |  |  |  | Check blank "Name on card " should not accept. | User should see error message "Enter your name exactly as it’s written on your card" after providing blank details. | Same as expected | Pass
252 |  |  |  | Check "Expiration date" field should accept only numeric values | User should be able to enter only numeric values in "Expiration date "field. | Same as expected | Pass
253 |  |  |  | Check "Expiration" field should not accept character values. | User should not able to enter character values in "Expiration date "field. | Same as expected | Pass
254 |  |  |  | Check "Expiration date" field length should accept only 6 numeric values | User should be able to enter "Expiration date" field length accept only 6 numeric values | Same as expected | Pass
255 |  |  |  | Check "Expiration date" field should accept MM/YYYY format | User should be able to enter date in "MM/YYYY" format | Same as expected | Pass
256 |  |  |  | Blank "Expiration date" field should not accept | "Expiration date" field should not accept blank it show error message "Enter a valid card expiry date" | Same as expected | Pass
257 |  |  |  | Check "Security Code" field should accept only numeric values | User should be able to enter only numeric values in "Security Code" field. | Same as expected | Pass
258 |  |  |  | Check "Security Code" field should not accept character values. | User should not able to enter character values in "Security Code" field. | Same as expected | Pass
259 |  |  |  | Check "Security Code" field length should accept only 4 numeric values | User should be able to enter "Security Code" field length accept only 4 numeric values | Same as expected | Pass
260 |  |  |  | Blank "Security Code" field should not accept | "Security Code" field should not accept blank show error message "Enter the CVV or security code on your card" | Same as expected | Pass
261 |  |  | Billing Address | User should see header | Select the address that matches your card or payment method. | Same as expected | Pass
262 |  |  |  | Check "Same as shipping address" checkbox | User should be able check on checkbox | Same as expected | Pass
263 |  |  |  | Check "Use a different billing address" checkbox | User should be able check on checkbox | Not available | Fail
264 |  |  |  | User should select only one check box. | User should be able check either "Same as shipping address" or "Use a different billing address" checkbox only one check box at one time. | Not available | Fail
265 |  |  |  | Check "Use a different billing address" field's. | User should see all saved address field. | Same as expected | Pass
266 |  |  |  | Below the check box user should see disclaimer | By submitting your information you confirm you have read and agree with the terms of our Privacy Policy and Legal Notice . | Same as expected | Pass
267 |  |  |  | Check "Return to shipping" link | After click on "Return to shipping" user should redirect on shipping page. | Same as expected | Pass
268 |  |  |  | Check "Pay now" button | Colour and font should be as per brand guidelines. | Not tested |  |  | Need card details
269 |  |  |  | After click on "Pay now" button payment should successfully done | User should see placed order details | Not tested |  |  | Need card details
270 |  |  |  | User should received email notification on his register email. | User should received order details on his email. | Not tested |  |  | Need card details
271 |  |  |  |  | User should see Shipping Address, Billing Address | Not tested |  |  | Need card details
272 |  |  |  |  | User should see product item, price, quantity and total. | Not tested |  |  | Need card details
273 |  |  |  | Check "Subtotal" | User should see product price | Not tested |  |  | Need card details
274 |  |  |  | Check "Shipping (Free Standard Shipping)" | User should see shipping charges if free it should show 0 | Not tested |  |  | Need card details
275 |  |  |  | Check "Tax (MN COUNTY TAX 0.15%)" | Tax should be calculated 0.15% of the product price | Not tested |  |  | Need card details
276 |  |  |  | Check "Tax (MN STATE TAX 6.875%)" | Tax should be calculated 6.875 % of the product price | Not tested |  |  | Need card details
277 |  |  |  | Check "Tax (MN SPECIAL TAX 0.5%)" | Tax should be calculated 0.5% of the product price | Not tested |  |  | Need card details
278 |  |  |  | Check "Total" | User should see final amount addition of subtotal + shipping + all taxes | Not tested |  |  | Need card details
279 |  | Check subscription buy | Check "Subscribe to Save" Buy | Check "Subscribe to Save" checkbox | User should be able to check "Subscribe to Save" checkbox. | Showing coming soon price is not visible | Pass
280 |  |  |  | "Subscribe to Save" check box should be available if Subscription plan is activated for the Product | User should be able to check "Subscribe to Save" | Same as expected | Pass
281 |  |  |  | After checking "Subscribe to Save" checkbox price will be change to a discounted price | User should be able to see price difference after checked "Subscribe to Save" checkbox. | Same as expected | Pass
282 |  |  |  | After cheking "Subscribe to Save" check box "Delivery every" drop down should be visible | User should be able to select specific "Deliver Every" frequency. | Not visible. | Fail
283 |  |  |  | Days mentioned in the delivery frequency dropdown for a subscription, should be as per what is mentioned in Recharge for the product with a recommended option | Delivery frequency and Days recommended should match with Recharge values | Same as expected | Pass
284 |  |  |  | After clicking on "Subscribe to Save" - "Save more on your subscription order with your Sight Matters coupon code." this tag line should be visible as per brand guideline colour and font. | User should be able to see "Save more on your subscription order with your Sight Matters coupon code." | Same as expected | Pass
285 |  |  |  | After click on "Add to Cart" button "My Cart" window should come on right side. | User should be able to see "My Cart" page details after click on "Add to Cart" button. | Same as expected | Pass
286 |  |  | Check "My Cart" page | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass
287 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Same as expected | Pass
288 |  |  |  | Check "Delivery Frequency" | User selected Delivery Frequency should be visible | Same as expected | Pass
289 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass
290 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
291 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via Recharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via Recharge") | Same as expected | Pass
292 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
293 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Delivery Frequency is not visible | Fail
294 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Same as expected | Pass
295 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity, delivery frequency | User should see all added products in the cart with details. | Same as expected | Pass
296 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass
297 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Remove button is available | Fail
298 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Not Visible | Fail
299 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | Same as expected | Pass
300 |  |  |  | Below of the added product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Same as expected | Pass
301 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
302 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass
303 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping and taxes will be completed securely via Recharge" | User should see tagline ""Shipping and taxes will be completed securely via Recharge" | Same as expected | Pass
304 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass
305 |  |  | Checkout | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass
306 |  |  |  | After click on "Checkout" button user should redirect to "Customer & Shipping Information" page | User should redirect to "Customer & Shipping Information" page | Same as expected | Pass
307 |  |  | Customer & Shipping Information | Customer should be able to fill "Customer & Shipping Information" Email fields. | "Email" field should accept alphanumeric and special character. | Same as expected | Pass
308 |  |  |  | Check blank "Email" should not accept. | "Email" field should not accept blank it should show "Please enter a valid email address" | Same as expected | Pass
309 |  |  | Order Summary | All product list should be visible those are customer selected for particular order. | User should see product list. | Same as expected | Pass
310 |  |  |  | Individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass
311 |  |  |  | User should see Subtotal, Shipping, Taxes, Total and Payment Due. | User should be able to see product price calculated values. | Same as expected | Pass |  | Apply button is available
312 |  |  | Use Promo code | After click on "Have a discount code? Enter it here" user should able to enter promo-code. | User should able to enter promo-code. | Same as expected | Pass
313 |  |  |  | After enter "Discount - code promo" click on "Ok" button. | After click on "Ok" button "Discount - code promo" should applied. | Same as expected | Pass |  | Error message is different
314 |  |  |  | Check blank "Discount - code promo" should not accept. | "Ok" button should not work after providing blank "Discount - code promo" | Same as expected | Pass
315 |  |  |  | Check if code is not valid it show error message "Unable to find a valid discount matching the code entered" | User should see error message after entered wrong code. | Same as expected | Pass
316 |  |  | Shipping Address | Check "Shipping Address" all fields it should accept alphanumeric and special character | All fields should accept alphanumeric and special character. | Same as expected | Pass
317 |  |  |  | Check "First name" field should accept alphanumeric and special character | User should be able to enter his "First name" | Same as expected | Pass
318 |  |  |  | Check "Last name" field should accept alphanumeric and special character | User should be able to enter his "Last name" | Company field is not available | Fail
319 |  |  |  | Check blank "Last name" should not accept it should show error message "Missing data for required field." | Blank "Last name" field should not accept. | Same as expected | Pass
320 |  |  |  | Check "Company" field should accept alphanumeric and special character | User should be able to enter his "Company" | Same as expected | Pass |  | Error message is different "Enter an address"
321 |  |  |  | Check "Address" field should accept alphanumeric and special character | User should be able to enter his "Address" | Same as expected | Pass
322 |  |  |  | Check blank "Address" should not accept it should show error message "Missing data for required field." | Blank "Address" field should not accept. | Same as expected | Pass
323 |  |  |  | Check "Apt, suite, etc." field should accept alphanumeric and special character | User should be able to enter his "Apt, suite, etc." | Same as expected | Pass |  | Error message is different "Enter a city"
324 |  |  |  | Check "City" field should accept alphanumeric and special character | User should be able to enter his "City" | Same as expected | Pass
325 |  |  |  | Check blank "City" should not accept it should show error message "Shorter than minimum length 1." | Blank "City" field should not accept. | Same as expected | Pass
326 |  |  |  | "City" field minimum 1 character length should not accept less character. | "City" field length should be minimum 1 character . | Same as expected | Pass
327 |  |  |  | Check "Country" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country" drop down. | Same as expected | Pass
328 |  |  |  | Check "State" field | User should see all State list in "State" drop down. | Same as expected | Pass |  | Error message is different "Enter a valid ZIP / postal code for United States"
329 |  |  |  | "Zip code" field should accept only numeric values. | Zip code field should accept only numeric values. | Same as expected | Pass |  | Error message is different "Enter a ZIP / postal code"
330 |  |  |  | "Zip code" field should not accept alphabetical and special character. | "Zip Code" should show "Invalid data: The US zip code must be the standard 5 digit number" when we enter alphabetical and special character. | Same as expected | Pass
331 |  |  |  | Blank "Zip code" field should not accept it show error message "Missing data for required field." | Blank "Zip Code" should not accept. | Same as expected | Pass
332 |  |  |  | Check "Phone" field should accept alphanumeric | User should be able to enter his "Phone" | Same as expected | Pass
333 |  |  |  | Check "Continue" button should be work with colour as per brand guidelines. | After click on "Continue" button user should redirect "Billing And Payment" page. | Same as expected | Pass
334 |  |  |  | After click on "Continue" button user should redirect to "Billing And Payment" page. | User should redirect "Billing And Payment" page. | Same as expected | Pass
335 |  |  | Payment page | "Customer & Shipping Information" visible on top of left side of the page. | User should be able to see "Customer & Shipping Information" details. | Same as expected | Pass |  | Checkbox is ecnomy and standard
336 |  |  |  | Check "Edit" link for "Customer & Shipping Information" | User should be able edit his "Customer & Shipping Information" with click on "Edit" link. | Same as expected | Pass
337 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Same as expected | Pass
338 |  |  | Billing And Payment | All card logo should be placed | User should see card logo. | Same as expected | Pass |  | Card number is not in as per existing site format
339 |  |  |  | Check "Name on card "should accept character and numeric values | "Name on card" field should accept character and numeric values. | Same as expected | Pass
340 |  |  |  | Check "Card number" field should accept only numeric values | User should be able to enter only numeric values in "Card number" field. | Same as expected | Pass
341 |  |  |  | Check "Card number" field should not accept character values. | User should not able to enter character values in "Card number" field. | Same as expected | Pass
342 |  |  |  | Check "Card number" field length should accept only 16 digit numeric values | User should be able to enter "Card number" length accept only 16 digit numeric values | Same as expected | Pass
343 |  |  |  | Blank "Card number" field should not accept it should show error massage (Your card number is incomplete.) | "Card number" field should not accept blank | Same as expected | Pass
344 |  |  |  | Check "Expiration" field should accept only numeric values | User should be able to enter only numeric values in "Expiration "field. | Same as expected | Pass
345 |  |  |  | Check "Expiration" field should not accept character values. | User should not able to enter character values in "Expiration "field. | Same as expected | Pass
346 |  |  |  | Check "Expiration" field length should accept only 4 numeric values | User should be able to enter Expiration" field length accept only 4 numeric values | Same as expected | Pass
347 |  |  |  | Blank "Expiration" field should not accept | "Expiration" field should not accept blank | Same as expected | Pass
348 |  |  |  | Check "CVV" field should accept only numeric values | User should be able to enter only numeric values in "CVV" field. | Same as expected | Pass
349 |  |  |  | Check "CVV" field should not accept character values. | User should not able to enter character values in "CVV" field. | Same as expected | Pass
350 |  |  |  | Check "CVV" field length should accept only 4 numeric values | User should be able to enter "CVV" field length accept only 4 numeric values | Not available | Fail
351 |  |  |  | Blank "CVV" field should not accept | "CVV" field should not accept blank
352 |  |  | Billing Address | Check previously added billing address should be visible and user should be able to check checkbox . | User should see previously added billing address and user should be able to check checkbox . | Same as expected | Pass
353 |  |  |  | User should check checkbox either previously added "billing address" or "Use a different billing address" check box. | User should check only one check box at one time. | Same as expected | Pass
354 |  |  |  | Check "Use a different billing address" check box. | After checked check box of "Use a different billing address" should open new page. | Same as expected | Pass
355 |  |  |  | Check "Billing Address" all fields it should accept alphanumeric and special character | All fields should accept alphanumeric and special character. | Same as expected | Pass
356 |  |  |  | Check "First name" field should accept alphanumeric and special character | User should be able to enter his "First name" | Same as expected | Pass
357 |  |  |  | Check "Last name" field should accept alphanumeric and special character | User should be able to enter his "Last name" | Company field is not available | Fail
358 |  |  |  | Check blank "Last name" should not accept it should show error message "Missing data for required field." | Blank "Last name" field should not accept. | Same as expected | Pass
359 |  |  |  | Check "Company" field should accept alphanumeric and special character | User should be able to enter his "Company" | Same as expected | Pass
360 |  |  |  | Check "Address" field should accept alphanumeric and special character | User should be able to enter his "Address" | Same as expected | Pass
361 |  |  |  | Check blank "Address" should not accept it should show error message "Missing data for required field." | Blank "Address" field should not accept. | Same as expected | Pass
362 |  |  |  | Check "Apt, suite, etc." field should accept alphanumeric and special character | User should be able to enter his "Apt, suite, etc." | Same as expected | Pass
363 |  |  |  | Check "City" field should accept alphanumeric and special character | User should be able to enter his "City" | Same as expected | Pass
364 |  |  |  | Check blank "City" should not accept it should show error message "Shorter than minimum length 1." | Blank "City" field should not accept. | Same as expected | Pass
365 |  |  |  | "City" field minimum 1 character length should not accept less character. | "City" field length should be minimum 1 character . | Same as expected | Pass
366 |  |  |  | Check "Country" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country" drop down. | Same as expected | Pass
367 |  |  |  | Check "State" field | User should see all State list in "State" drop down. | Same as expected | Pass
368 |  |  |  | "Zip code" field should accept only numeric values. | Zip code field should accept only numeric values. | Same as expected | Pass
369 |  |  |  | "Zip code" field should not accept alphabetical and special character. | "Zip Code" should show "Invalid data: The US zip code must be the standard 5 digit number" when we enter alphabetical and special character. | Same as expected | Pass
370 |  |  |  | Blank "Zip code" field should not accept it show error message "Missing data for required field." | Blank "Zip Code" should not accept. | Same as expected | Pass
371 |  |  |  | Check "Phone" field should accept alphanumeric | User should be able to enter his "Phone" | Same as expected | Pass
372 |  |  |  | Check check-box below of the billing address | User should be able to check our unchecked below billing address check-box "Yes, I would like to receive promotional communications from Bausch + Lomb." | Same as expected | Pass
373 |  |  |  | Check disclaimer | "By clicking "Place my order", you confirm that your subscription will automatically renew and your credit card will automatically be charged the subscription price according to the Order summary section of this page until you cancel your subscription. You also authorize PreserVision to charge the supplied payment method, or another payment method on file, for the subscription price on each renewal. You can cancel your subscription at any time." | Same as expected | Pass
374 |  |  |  | Check "Place my order" button | User should be able to click "Place my order" button with colour as per brand guidelines. | Same as expected | Pass
375 |  |  |  | After click on "Place my order" button order should placed successfully. | User order should placed successfully after click on "Place my order" button | Same as expected | Pass
376 |  |  |  | Check email notification | After order placed user should received email notification on his email. | Same as expected | Pass
377 |  | Check product both buy option | Check both "Subscribe to Save" and "One Time Purchase" buy | Select product in the cart one is "subscribe to save" and other is "One time purchase"
378 |  |  | Check "My Cart" page | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass
379 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Not visible | Fail
380 |  |  |  | Check "Delivery Frequency" | If user "Subscribe to Save" selected product below Delivery Frequency should be visible | Not available | Fail
381 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass
382 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
383 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via ReCharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via ReCharge") | Same as expected | Pass
384 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
385 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass
386 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Not visible | Fail
387 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity, delivery frequency | User should see all added products in the cart with details. | Blank fields availble | Fail
388 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Not available | Fail
389 |  |  |  | Check subscribe to save product details | If product selected subscribe to save below "Delivery Frequency" should be visible. | Same as expected | Pass
390 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Not available | Fail
391 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass
392 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | Same as expected | Pass
393 |  |  |  | Below of the added product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Same as expected | Pass
394 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass
395 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass
396 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping and taxes will be completed securely via Recharge" | User should see tagline ""Shipping and taxes will be completed securely via Recharge" | Not available | Fail
397 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass
398 |  |  |  | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass
399 |  |  |  | After click on "Checkout" button user should redirect to "Customer & Shipping Information" page | User should redirect to "Customer & Shipping Information" page | Same as expected | Pass
400 |  |  | Customer & Shipping Information | "Customer & Shipping Information" visible on top of left side of the page. | User should be able to see "Customer & Shipping Information" details. | Same as expected | Pass
401 |  |  |  | Check "Edit" link for "Customer & Shipping Information" | User should be able edit his "Customer & Shipping Information" with click on "Edit" link. | Same as expected | Pass
402 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Same as expected | Pass
403 |  |  | Order Summary | All product list should be visible those are customer selected for particular order. | User should see product list. | Same as expected | Pass
404 |  |  |  | Individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass
405 |  |  |  | User should see Subtotal, Shipping, Taxes, Total and Payment Due. | User should be able to see product price calculated values. | Same as expected | Pass
406 |  |  |  | Check "taxes" | taxes should be calculated 7.5% of the product price. | Not available | Fail
407 |  |  |  | Check "Total" | "Total" should be addition of Subtotal, Shipping and Estimated taxes | Same as expected | Pass
408 |  |  |  | Check "Payment Due" | "Payment Due" should be addition of Subtotal, Shipping and Estimated taxes
409 |  |  | Use Promo code | After click on "Have a discount code? Enter it here" user should able to enter promo-code. | User should able to enter promo-code.
410 |  |  |  | After enter "Discount - code promo" click on "Ok" button. | After click on "Ok" button "Discount - code promo" should applied.
411 |  |  |  | Check blank "Discount - code promo" should not accept. | "Ok" button should not work after providing blank "Discount - code promo"
412 |  |  |  | Check if code is not valid it show error message "Unable to find a valid discount matching the code entered" | User should see error message after entered wrong code.
413 |  |  | Billing And Payment | All card logo should be placed | User should see card logo.
414 |  |  |  | Check payment fields. | Check all credit card field's.
415 |  |  | Billing Address | Check all billing address fields. | User should be able to enter all details in billing field's.
416 |  |  |  | Check check-box below of the billing address | User should be able to check our unchecked below billing address check-box "Yes, I would like to receive promotional communications from Bausch + Lomb."
417 |  |  |  | Check disclaimer | "By clicking "Place my order", you confirm that your subscription will automatically renew and your credit card will automatically be charged the subscription price according to the Order summary section of this page until you cancel your subscription. You also authorize PreserVision to charge the supplied payment method, or another payment method on file, for the subscription price on each renewal. You can cancel your subscription at any time."
418 |  |  |  | Check "Place my order" button | User should be able to click "Place my order" button with colour as per brand guidelines.
419 |  |  |  | After click on "Place my order" button order should placed successfully. | User order should placed successfully after click on "Place my order" button
420 |  |  |  | Check email notification | After order placed user should received email notification on his email.
421 | Checkout | Checkout Scenario | Sold-out | Check if product is not available it should show "Temporarily Unavailable" | If product is not available it should show "Temporarily Unavailable" with colour as per brand guidelines.
422 |  |  | Abandoned Cart | User may have received abandoned cart emails notification on his registered email. | User should see abandoned cart notification email
423 |  |  | Request for Cancellation of Subscription | User should be able to cancel subscription. | After click on "Manage Your Subscriptions" button user should be able to cancel subscription.
424 | Integration Scenarios | KH Integration Scenario | Authentication API | Check Authentication is occurred via Knipper | Authentication is done by via Knipper. | Same as expected | Pass
425 |  |  |  | Check the Authentication API header ClientID, client secret, grant type and resource | Values should be accepted | Same as expected | Pass
426 |  |  |  | Check Shopify token request to Knipper with all variable. | Request token should be send to Knipper | Same as expected | Pass
427 |  |  |  | Check Knipper token response to Shopify with all variable.( access token, token type, expires in, extemporising, expires on, not before and resource) | Token response should be come in Shopify end with all field's. | Same as expected | Pass
428 |  |  |  | Check Authentication response "200-ok " if success | If success response should be come "200-ok" | Same as expected | Pass
429 |  |  |  | Check Authentication response "404 - Not Found " if failed | If failed response should be come "404 - Not Found" | Same as expected | Pass
430 |  |  | Order API | Check Shopify order details request to Knipper with all variables. | Order details request should send to Knipper with all field's | Same as expected | Pass
431 |  |  |  | Check Knipper response with response code | Every time Knipper response should come in code either"200-ok" or "404- Not Found". | Same as expected | Pass
432 |  |  |  | Check order should send to Knipper this format Email, first name, last name, company, address, apartment, suite, city, country, state, zip code, phone, suffix, salutation, designation, attention to, Item code and quantity | Order format should match | Same as expected | Pass
433 |  |  | Order Status API | Check Knipper order status details response to Shopify . | Order status response should be come at Shopify end. | Awaiting Status from Knipper | Fail
434 |  |  |  | Shopify will send the values to Knipper (one-time) that will be used for the Authentication API header (ClientID, client secret, grant type and resource) | Authentication values should be same those Shopify shared to Knipper | Awaiting Status from Knipper | Fail
435 |  |  |  | Knipper to send request for a token using the above values | Shopify shared values should Knipper use for token request. | Awaiting Status from Knipper | Fail
436 |  |  |  | Check Order Status change done by Knipper | Order status is done by via Knipper. | Awaiting Status from Knipper | Fail
437 |  |  |  | Check Knipper will send the Order Status details to Shopify after the above token is accepted with the following fields. ( Order: Status Description, Order Number: Request ID, Tracking Number: Tracking Number, Tracking Company: Courier Name) | Order status format should be match. | Awaiting Status from Knipper | Fail
438 |  |  |  | Check order status should send emails notification on his registered email | Order status should come on registered email. | Awaiting Status from Knipper | Fail
439 | PG Integration Scenario | Payment Response | Contact information and Shipping address | Check all fields should accepts alphanumeric Email, first name, last name, company, address, apartment, suite, city, country, state, zip code, phone. | All fields should accept alphanumeric and special character.
440 |  |  |  | Check Payment, Billing address after providing correct all card details payment should be successful done. | After providing correct card details payment should be successfully done.
441 |  |  |  | Check after successfully payment done system should send emails notification on his registered email | Payment done notification should be send on customer email.
442 |  |  |  | Check after providing wrong card details systems should show error message (Your payment details couldn’t be verified. Check your card details and try again.) | Wrong card details should not accept.
443 | Replacement Order | Check Replacement Order | Check Order Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | There should be an older order reference in "Notes" for each Replacement Order | Same as expected | Pass
444 |  |  | Check Product Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | The replacement order should have a reference to the Product(s) that have been ordered before | Same as expected | Pass
445 |  |  | Customer Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | The replacement order should be done for the Customer for whom there is an elaready existing paid order | Same as expected | Pass
446 |  |  | Check Amount | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Replacement Order amount should always be ZERO and does not pass through the payment gateway | Same as expected | Pass
447 |  |  | Check Address | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Replament order should have a Shipping address that can be similar to the existing Order or can also be different | Same as expected | Pass
448 |  |  | Check Tagging | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Each replacement order should be tagged as "Replacement" under the field "Tags" | Same as expected | Pass
449 | Data Migration | Import Products | All Active Products | Check Product counts
450 |  |  |  | Check Product Information and Media
451 |  |  |  | Set Product Inventory
452 |  |  | All Draft Products | Check Product counts
453 |  |  |  | Check Product Information and Media
454 |  |  |  | Set Product Invetory
455 |  | Import Customers | All Customers | Check Customer Count
456 |  |  |  | Check Customer Information (randomly)
457 |  | Import Transactions | All Transactions | Check Transaction counts
458 |  |  |  | Check Transaction values (randomly and in aggregation)
459 |  | Import Orders (Single Buy) | All Single Buy Orders | Check Order counts
460 |  |  |  | Check Order Details (randomly)
461 |  | Import Orders (Subscriptions) | All Subscriptions | Check Order counts
462 |  |  |  | Check Order Details (randomly)
463 |  |  |  | Check Cusmtore Detals (randomly)
464 |  | Import Discount Codes | All Discount Codes | Check Discount Code count
465 |  |  |  | Check Active Discount Code settings (randomly)
466 |  |  |  | Check if Discounyt Code works
467 |  | Import Gift Cards | All Gift Cards | Check Gift Cards count
468 |  |  |  | Check an active Gift Card's settings (randomly)
469 |  |  |  | Check if an active Gift Card works (randomly)