## Test Schedule
Shopify Consumer E-Commerce
| Phase | Start Date | End Date | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | Primary Responibility | Resources
5 | System Integration Testing | 2023-02-20 | 2023-03-17 | [9 empty] | AR | CP, MP, VK, AJ | bar: 2023-02-10 to 2023-03-17
6 | UAT | 2023-03-13 | 2023-03-31 | [9 empty] | AR | CP, MP, VK, AJ | bar: 2023-03-17 to 2023-03-31
Week Ending
Index | Tasks | Start Date | End Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | RESOURCES
5 | System Integration Testing | 2023-02-20 | 2023-03-17 | 2023-02-10 | 2023-02-17 | 2023-02-24 | 2023-03-03 | 2023-03-10 | 2023-03-17 | 2023-03-24 | 2023-03-31 | 2023-04-07 | Primary Responibility | Resources
5.01 | Test Environment Setup | 2023-02-20 | 2023-02-23 | [9 empty] | CP | CP, MP, VK, AJ | bar: Week Ending 3
5.02 | Creation of SIT Test Plan | 2023-02-06 | 2022-02-17 | [9 empty] | AR | AR, CP, MP | bar: Week Ending 1 to Week Ending 2
5.03 | Creation Of SIT Test Scenarios | 2023-02-06 | 2022-02-17 | [9 empty] | AR | AR, CP, MP | bar: Week Ending 1 to Week Ending 2
5.04 | Creation of SIT Test Scripts | 2023-02-06 | 2022-02-17 | [9 empty] | AR | AR, CP, MP | bar: Week Ending 1 to Week Ending 2
5.05 | Send SIT Test Scripts Review and Feedback | 2023-02-20 | 2023-02-20 | [9 empty] | AR | AR, RM, EC | bar: Week Ending 3
5.06 | SIT Test Scripts Signoff | 2022-02-24 | 2022-02-24 | [9 empty] | RM | RM, EC | bar: Week Ending 3
5.07 | Data Setup for SIT 1 | 2022-02-24 | 2022-02-24 | [9 empty] | AR | VK, AJ, MP | bar: Week Ending 3
5.08 | SIT 1 Execution | 2023-02-27 | 2023-03-07 | [9 empty] | AR | AR | bar: Week Ending 4 to Week Ending 5
5.09 | User Scenarios | 2023-02-27 | 2023-03-01 | [9 empty] | AR | AR, MP | bar: Week Ending 4 to Week Ending 5
5.10 | PG Scenarios | 2023-02-27 | 2023-03-01 | [9 empty] | AR | AR, MP | bar: Week Ending 4 to Week Ending 5
5.11 | Knipper Scenarios | 2023-02-27 | 2023-03-01 | [9 empty] | AR | AR, MP | bar: Week Ending 4 to Week Ending 5
5.13 | Bug Fixes | 2023-03-02 | 2023-03-07 | [9 empty] | AR | CP, VK, AJ | bar: Week Ending 4 to Week Ending 5
5.14 | Data Setup for SIT 2 | 2023-03-06 | 2023-03-07 | [9 empty] | AR | VK, AJ, MP | bar: Week Ending 4 to Week Ending 5
5.15 | SIT 2 Execution | 2023-03-08 | 2023-03-17 | [9 empty] | AR | bar: Week Ending 5 to Week Ending 6
5.16 | User Scenarios | 2023-03-08 | 2023-03-10 | [9 empty] | AR | AR, MP | bar: Week Ending 5 to Week Ending 6
5.17 | PG Scenarios | 2023-03-08 | 2023-03-10 | [9 empty] | AR | AR, MP | bar: Week Ending 5 to Week Ending 6
5.18 | Knipper Scenarios | 2023-03-08 | 2023-03-10 | [9 empty] | AR | AR, MP | bar: Week Ending 5 to Week Ending 6
5.20 | Bug Fixes | 2023-03-13 | 2023-03-16 | [9 empty] | AR | CP, VK, AJ | bar: Week Ending 5 to Week Ending 6
5.21 | Submit SIT Results for Approval | 2023-03-10 | 2023-03-10 | [9 empty] | AR | AR, MP | bar: Week Ending 6
5.22 | Get SIT sign off from client | 2023-03-17 | 2023-03-17 | [9 empty] | RM | RM, EC | bar: Week Ending 6
6 | UAT | 2023-03-13 | 2023-03-31 | [9 empty] | AR | bar: Week Ending 6 to Week Ending 8
6.01 | System Data Refresh (Partial IDL) | 2023-03-13 | 2023-03-13 | [9 empty] | AR | AR | bar: Week Ending 6
6.02 | Creation of UAT Test Plan | 2023-03-13 | 2023-03-15 | [9 empty] | AR | MP | bar: Week Ending 6
6.03 | Creation Of UAT Test Scenarios | 2023-03-13 | 2023-03-15 | [9 empty] | AR | MP | bar: Week Ending 6
6.04 | Creation of UAT Test Scripts | 2023-03-13 | 2023-03-15 | [9 empty] | AR | MP | bar: Week Ending 6
6.05 | Submit UAT Test Script for Approval | 2023-03-15 | 2023-03-15 | [9 empty] | AR | AR | bar: Week Ending 6
6.06 | Get UAT Test Script Approval | 2023-03-17 | 2023-03-17 | [9 empty] | RM | RM, EC | bar: Week Ending 6
6.07 | UAT 1 Execution: | 2022-03-20 | 2022-03-24 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 7
6.08 | UAT 1 Execution: User Stories | 2022-03-20 | 2022-03-21 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 7
6.09 | UAT 1 Execution: Managed Services Stories | 2022-03-20 | 2022-03-21 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 7
6.10 | UAT 1 Bug Fixes | 2023-03-22 | 2023-03-24 | [9 empty] | AR | CP, VK, AJ | bar: Week Ending 7
6.11 | Sumbit for PRC Approval 3 | 2023-03-24 | 2023-03-24 | bar: Week Ending 7
6.11 | UAT 2 Execution: | 2023-03-27 | 2023-03-31 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 8
6.12 | UAT 2 Execution: User Stories | 2023-03-27 | 2023-03-28 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 8
6.13 | UAT 2 Execution: Managed Services Stories | 2023-03-27 | 2023-03-28 | [9 empty] | RM | NEED UAT TESTERS | bar: Week Ending 8
6.14 | UAT 2 Bug Fixes | 2023-03-29 | 2023-03-31 | [9 empty] | AR | CP, VK, AJ | bar: Week Ending 8
6.15 | Submit UAT results for Sign off | 2023-03-28 | 2023-03-28 | [9 empty] | AR | AR | bar: Week Ending 8
6.16 | Get UAT Sign off from the client | 2023-03-31 | 2023-03-31 | [9 empty] | RM | RM, EC | bar: Week Ending 8

## Test Scenarios
Shopify Consumer E-Commerce
CONSUMER SCENARIOS |  | FULFILMENT, INVENTORY & REPLACEMENT SCENARIOS
Scenario Category | Test Scenario | Scenario Category | Test Scenario
Static Pages | Home Page(header, mast and collection) | Fulfilment (with KH) | Authentication API
| Browse to all Footer pages |  | Order API
| Unsubscribe Bar check (for opt-outs) |  | Order Status API
Login | User Login (positive + negative) | Inventory Management | Update Inventory (manual)
| Forgot Password (positive + negative) |  | Mark Threshold for "Out of Stock"
| User Registration (positive + negative) |  | Get Inventory Report
My Account Page | Logout | Check Replacement Order | Check Order Reference
| User Details |  | Check Product Reference
| Subscriptions |  | Customer Reference
| Get Subscription Access |  | Check Amount
| Manage your Subscriptions |  | Check Address
| View Default Address |  | Check Tagging
Manage Address
| Order History | DATA MIGRATION SCENARIOS
| Request for Replacement Order | Scenario Category | Test Scenario
Product Browsing | Check Product Page all elements | Import Products | Check Product counts
| Product Marketing Information Section |  | Check Product Information and Media
| Shop Our Other Products |  | Set Product Inventory
| Product Quantity Check |  | Check Product counts
| Product Inventory Check |  | Check Product Information and Media
| Submit Customer review (submission only) |  | Set Product Invetory
| Report Inapproprite Review | Import Customers | Check Customer Count
Single buy | Check "One Time Purchase" Buy |  | Check Customer Information (randomly)
| Check "My Cart" page | Import Transactions | Check Transaction counts
| Check "Shopping Cart" page |  | Check Transaction values (randomly and in aggregation)
| Contact information | Import Orders (Single Buy) | Check Order counts
| Order Summary |  | Check Order Details (randomly)
| Shipping Address | Import Orders (Subscriptions) | Check Order counts
| Payment page |  | Check Order Details (randomly)
| Billing Address |  | Check Cusmtore Detals (randomly)
Subscription buy | Check "Subscribe to Save" Buy | Import Discount Codes | Check Discount Code count
| Check "My Cart" page |  | Check Active Discount Code settings (randomly)
| Check "Shopping Cart" page |  | Check if Discounyt Code works
| Checkout | Import Gift Cards | Check Gift Cards count
| Customer & Shipping Information |  | Check an active Gift Card's settings (randomly)
| Order Summary |  | Check if an active Gift Card works (randomly)
Use Promo code
Shipping Address
Payment page
Billing And Payment
Billing Address
Checkout (Others) | Sold-out
Abandoned Cart
Request for Cancellation of Subscription
Payment | Payment Response Positive
Payment Response Negative

## Comments & Questions (rlm)
# | Question / comment … | Include (y/n) | Column1
1 | anything that needs to be tested after KH enters a replacement order? | y | Test 443-448
2 | Refunds - to ensure the order and refund is properly reflected in Shopify | ?
3 | Data: how will we ensure all data loaded is complete and correct before launch? | y | Test 449-470
4 | Data integration: checks to ensure the data being sent and received is complete, correct and can be loaded by the receiving party. | y | Test 449-470
5 | is multifactor signin required to be offered per IT Sec guidance? | n
6 | Password strength consisent with IT Sec guidance? Need to determine of password spec from B+L can be enabled in Shopify. | n (inform IT Sec)
7 | TC 71 - minimum of 5 characters seems too short. Consistent with IT Sec guidance? | ? Investigate - what dope IT Sec call for?
8 | TC 79, … andothers related to subscriptions. I don't see anythign regardign payment options and shipping. | Ahmad to check it is already included. | Test 316-334
9 | If a user is not registered, but has placed an order, are enabling them to go back and view the status of the order? If so, do we have a TC for this ? No - to track order history need to register. | No
10 | TC 132 - should we disable replacement orders for all but KH? Do we want the consumer to have this optoin? Is it avaialble to consumers on the current site? | y | Only designated KH users. Investigating
11 | TC 132. Should we have a set of cases defined to test the full cycle from request, through processing of the replacement order, or as much as possible to ensure it is working as expected and is reflected apprporiately in shopify? | y | Request for replacement will g to KH. Checking Replacement Order will done by Shopify Team through Test 316-334
12 | Marketplace testing: Do we have TCs specific to the marketplace, where functionality would be different? E.g., "shop our other products", etc. | handled
13 | What's the difference between Shopping Cart and My Cart (TC 191 and 203)? | my cart "drawer" - check other references
14 | TC 217 - maybe wordsmith it. Not clear. | Ahmad | Re-phrased
15 | Is 217 only avaialble for registered users who logged in? If so, we may want cases for non-registered users who return and want status of their order, ability to view products in order, etc. | Not available except for registered users
16 | May be appopriate to add TCs related to not entering invalid info in required fields and trying to continue with the order. E.g., 229, 241, 261 (shipment info, payment info), etc. | double check if negative testing is applied throughout. Believe so.
17 | TC 279 (Subscribe and Save) - does the user need to be a registered user to select subscribe and save? If not, are there subsequent actions that need to occur to registerd, add payment info, etc.? | no need to register
18 | General coverage comment: I don't believe we specify the site eahc TC will be run against. Do we need to run all of them against all 4 storefronts? Does Markdetplace have a different or unique set of TCs as it offers all products and a few other differences? | anseered, run against all sites. Columns setup to right.
19 | How do we verify Avalara AvaTax is setup correctly and that monthly reports generated will support filing and remittance? | pursue (y).
20 | How do we verify SignifyD is setup correctly? When orders are flagged as fraudulent and not processed, do we reflect it in order historh appropriately. Any notifications that we could then use to follow up on if necessary. What reports will be avaialble from SignifyD? | pursue (y).

## Test Cases & Results
Shopify Consumer E-Commerce
[6 empty] | Bio true | [5 empty] | Lumify
Test Case # | Section | Scenario | Test Case | Test Steps | Expected results | Actual result | Pass / Fail | Test Date | Tester Comment | Developer Comment | Status | Actual result | Pass / Fail | Test Date | Tester Comment | Developer Comment | Status
1 | Static Pages | Home Page(header, mast and collection) | Header check | Top line colour should be as per the brand guidelines | Home page top line colour should be dark blue. | Same as Expected | Pass | 2023-02-27
2 |  |  |  | All Logo Placement should be as per the guidelines. | All home page logo should placed on the top left | Same as Expected | Pass | 2023-02-27
3 |  |  |  | Product Dropdown should be visible with all product list. | Product dropdown should be visible with all related brand products. Marketplace should have all brands listed in the dropdown | Same as Expected | Pass | 2023-02-27
4 |  |  |  | The link to Login should work fine user should redirect to login page. | After click on login button user should redirect to login page. | Same as Expected | Pass | 2023-02-27
5 |  |  |  | The link to Cart should work fine user should redirect to my cart page. | After click on cart button user should redirect to my cart page. |  | Fail | 2023-02-27 | Empty my cart page is not properly build.(Please check My Cart header, Continue Shopping link)
6 |  |  |  | Cart: Num of items | Number of items should be shown next to the cart icon | Shows as cart empty instead of adding item to cart. Not visible. | Fail | 2023-02-27 | Unable to add items to cart
7 |  |  | Marketing Banner (mast) check | Num of items in a banner | All Marketing mast images should be visible on home page |  | Pass | 2023-02-27
8 |  |  |  | Working of carousel | Crousel navigation should work when the user presses the left and right buttons | Crousel not available | Fail | 2023-02-27
9 |  |  | Product Collections Check | Disclaimer available at the top of the collections | Disclaimer "*These statements have not been evaluated by the Food and Drug Administration. These products are not intended to diagnose, treat, cure or prevent any disease." available at the top of the collections | Disclaimer not visible | Fail | 2023-02-27
10 |  |  |  | Check Product list | 3 products should be visible | Same aas expected | Pass | 2023-02-27
11 |  |  |  | Product individual check. | Clicking on any link on particular product, the user should be able to view selected product details on the Products page |  | Pass | 2023-02-27
12 |  |  |  | Product One Time Price Check | Product one time pricing shown in collections should be correct |  | Pass | 2023-02-27
13 |  |  |  | Product Subscription Price Check | Product subscription pricing shown in collections should be correct | Coming Soon | Fail | 2023-02-27 | Subsription not yet available
14 |  | Browse to all Footer pages | Check "Learn" link | Check "Privacy Policy" link | After click on "Privacy Policy" link new pop up should come on the page. | Same as ExpectedRedirects to new page with privacy policy | Pass | 2023-02-27
15 |  |  |  | Check Pop up window | "Just A Moment... This link takes you to another site at www.bauschhealth.com. Do you want to proceed? | No pop up window appears with "Just A Moment" message | Fail | 2023-02-27
16 |  |  |  | Check "Cancel" button | After click on "Cancel" button user should go back to his current page. | No pop up window appears with "Just A Moment" message | Fail | 2023-02-27
17 |  |  |  | Check cross sign | After click on cross sign pop up should close | No pop up window appears with "Just A Moment" message | Fail | 2023-02-27
18 |  |  |  | Check "Take Me There" button | After click on "Take Me there" button user should redirect to "Privacy Policy" page. | No pop up window appears with "Just A Moment" message | Fail | 2023-02-27
19 |  |  |  | The link to Refund Policy should work fine | User should able to redirect refund policy page. | Same as expected | Pass | 2023-02-28
20 |  |  |  | The link to Customer Care should work fine | User should able to redirect customer care page. | Same as expected | Pass | 2023-02-28
21 |  |  |  | The link to Subscriptions FAQ should work fine | User should able to redirect subscriptions faq page. | Same as expected | Pass | 2023-02-28
22 |  |  |  | The link to Contact Us should work fine | User should able to redirect contact us page. | Same as expected | Pass | 2023-02-28
23 |  |  |  | The link to Legal Notice should work fine | User should able to redirect legal notice page. | Same as expected | Pass | 2023-02-28
24 |  |  | Contact Us | Check "Contact Us" link should available | User should be able to click on "Contact Us" link. | Same as expected | Pass | 2023-02-28
25 |  |  |  | After click on "Contact Us" link user should redirect to "Contact Us" page. | User should be able to see all "Contact Us" page description. | Same as expected | Pass | 2023-02-28
26 |  |  |  | Brand "Contact number" and "email_id" should be visible | User should be able to see company "Contact Details". | Same as expected | Pass | 2023-02-28
27 |  |  |  | "Hours of Operation: Monday thru Friday 8:00 am to 8:00 pm EST" User should see this details on "Contact Us" page | User should see this details. |  |  | 2023-02-28
28 |  |  |  | "Name" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as Expected | Pass | 2023-02-28
29 |  |  |  | "Email" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as Expected | Pass | 2023-02-28
30 |  |  |  | After providing wrong email it should show error message "Email is invalid" | Email field should not accept wrong email it should show error message. | Takes any input. | Fail | 2023-02-28 | Only check for "@" symbol in the input. Accepts anything with the symbol
31 |  |  |  | Blank "Email" field should not accept | User should not able blank to provide blank "Email" field. | Same as expcted | Pass | 2023-02-28
32 |  |  |  | "Phone Number" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. | Same as expcted | Pass | 2023-02-28
33 |  |  |  | "Message" field should accept alphanumeric and special character. | User should be able to enter alphanumeric and special character. |  |  | 2023-02-28
34 |  |  |  | Blank "Message" field should not accept | User should not able to provide blank "Message" field it show error message " Please fill out this field" | Same as expected | Pass | 2023-02-28
35 |  |  |  | Check after click on "Privacy Policy" link user should redirect to "PRIVACY POLICY" page. | User should redirect to "https://www.bauschhealth.com/privacy" |  | Pass | 2023-02-28
36 |  |  |  | Check after click on "Legal Notice" link user should redirect to "LEGAL NOTICE" page. | User should redirect to "https://www.bauschhealth.com/terms" |  | Pass | 2023-02-28
37 |  |  |  | Check "Submit" button | "Submit" button should be visible with the colour as per the brand guideline | Instead of "Submit" the button says "Contact" | Fail | 2023-02-28 | Instead of "Submit" the button says "Contact"
38 |  |  |  | User should be able to click on "Submit" button. | After click on "Submit" button it should show "Thanks for contacting us. We'll get back to you as soon as possible" | Same as expected | Pass | 2023-02-28
39 |  |  |  | After providing all "Contact Us" page details "Submit button" should work. | User need to provide all "Contact Us" page detail before click on "Submit" button. | Button works | Pass | 2023-02-28 | Instead of "Submit" the button says "Contact"
40 |  |  | Check "Shop" links | The link to AREDS 2 Soft Gels should work fine | User should able to redirect areds 2 soft gels page. | This link unavailable | Fail | 2023-02-28
41 |  |  |  | The link to AREDS 2 Chewables should work fine | User should able to redirect areds 2 Chewables page. | This link unavailable | Fail | 2023-02-28
42 |  |  |  | The link to AREDS2 + Multivitamin should work fine | User should able to redirect areds2 + multivitamin page. | This link unavailable | Fail | 2023-02-28
43 |  |  | Check "Account" link | The link to Log In should work fine | User should able to redirect log in page. | Same as expected | Pass | 2023-02-28
44 |  |  |  | The link to Register should work fine | User should able to redirect register page. | Same as expected | Pass | 2023-02-28
45 |  |  |  |  | User should able to redirect do not sell my personal information page. | Same as expected | Pass | 2023-02-28
46 |  |  | Check all Footer details. | Footer line colour | Footer line colour should be as per brand guidelines | Same as expected | Pass | 2023-02-28
47 |  |  |  | Footer disclaimer check | Footer disclaimer should be visible and correct | Same as expected | Pass | 2023-02-28
48 |  |  |  | Check California residents link. The link to Do not sell my personal information should work fine | After click on link user should be able to redirect to "California residents" page | Not available | Fail | 2023-02-28
49 |  |  |  | Payment getway logo | All payment logo should be visible in footer page. | Same as expected | Pass | 2023-02-28
50 |  | Unsubscribe Bar check | Check all opt-outs | Unsubscribe | User should be directed to https://cloud.marketing.bausch.com/Privacy-Page-Unsubscribe | Same as expected | Pass | 2023-02-28
51 |  |  |  | Do Not Sell or Share My Personal Information | User should be directed to https://cloud.marketing.bausch.com/do-not-sell-or-share | Same as expected | Pass | 2023-02-28
52 |  |  |  | Do Not Target | User should be directed to https://cloud.marketing.bausch.com/do-not-target | Same as expected | Pass | 2023-02-28
53 |  |  |  | Limit the Use of My Sensitive Personal Information | User should be directed to https://cloud.marketing.bausch.com/Limit-Sensitive-Personal-Information-Usage | Same as expected | Pass | 2023-02-28
54 | Login | User Login (positive + negative) | Check "Sign In" button | User should be logged into the account after providing correct email and password. | After click on sign in button with correct email & password user should be able to login. | Same as expected | Pass | 2023-02-28
55 |  |  |  | By providing wrong email user should not be able to log-in. It should show error message (Incorrect email or password). | User should not be logged after entered wrong email id | Same as expected | Pass | 2023-02-28
56 |  |  |  | By providing wrong password user should not be able to log-in. It should show error message (Incorrect email or password). | User should not be logged after entered wrong password | Same as expcted | Pass | 2023-02-28
57 |  |  |  | Colour of "Sign In" button colour should be as per the brand guidelines | Sign In button colour should be as per the brand guidelines | Same as expected | Pass | 2023-02-28
58 |  |  |  | After click on "sign In" button with correct credentials user should redirect "My Account" page. | User should be able to see "My Account" page details. | Same as expected | Pass | 2023-02-28
59 |  | Forgot Password (positive + negative) | Check Forgot your password button | Login page "Forgot Your Password" link should be available next to the "Sign In" button | After click on forgot your password user should be able to redirect forgot password page. | Same as expected | Pass | 2023-02-28
60 |  |  |  | User should be able to enter register email & after click on "Recover Password" user should received reset your password link on his register email | Forgot password link should received on user register email | No email received | Fail | 2023-02-28
61 |  |  |  | Cancel link should be available on Forget your password page. | After click on Cancel link user should able to back to login page. | Button unavailable | Fail | 2023-02-28
62 |  |  |  | Provided email address should be pre-registered | Provided email address should be registered otherwise show error message "No account found with that email" | Accepted non registered email | Fail | 2023-02-28
63 |  |  |  | Provided email address should be in correct format | Provided email address should be in correct format otherwise show error message "No account found with that email" | Accepts email without domain | Fail | 2023-02-28
64 |  | User Registration (positive + negative) | Check Register button | Click on register button user should be redirect to Create account page. | User should able redirect to Create account page. | Same as expected | Pass | 2023-02-28
65 |  |  | Check Create button | User should be able to enter first name, last name, email and password. | User should able to fill all create account page details. | Same as expected | Pass | 2023-02-28
66 |  |  |  | Successful user account creation | After providing correct user details, user account should be created. | User is redirected to login page | Fail | 2023-02-28 |  |  |  | Once the account is created, the user is redirected to the brand home page and logged in
67 |  |  |  | First Name should not be blank | Provide blank First Name | Same as expected | Pass | 2023-02-28
68 |  |  |  | Last Name should not be blank | Provide blank Last Name | Same as expected | Pass | 2023-02-28
69 |  |  |  | Email Address should not be blank | Provide blank Email Address | Same as expected | Pass | 2023-02-28
70 |  |  |  | Passwords must be a minimum of 5 characters long and special characters are allowed. | Password field only accept more than 5 characters and special characters. | Same as expected | Pass | 2023-02-28
71 |  |  |  | Password field not accept 4 character password it should show error message (Password is too short (minimum is 5 characters). | Password field not accept 4 character password it should show error message. | Same as expected | Pass | 2023-02-28
72 |  | My Account Page | Logout | Check "Logout" link user should be able to logout. | After click on "Logout" link user should be logout. | Same as expected | Pass | 2023-02-28
73 |  |  |  |  | User to be redirected to the Homepage (Marketplace) | User is directed to accounts's page | Fail | 2023-02-28
74 |  |  | User Details | Name should be as per what was submitted at the time of the user creation | User should see submitted user name | Same as expected | Pass | 2023-02-28
75 |  |  |  | Email Address should be as per what was submitted at the time of the user creation | User should see submitted Email address | Same as expected | Pass | 2023-02-28
76 |  |  |  | Default Address should be as per what was submitted at the time of the user creation | User should see submitted default address | Same as expected | Pass | 2023-02-28
77 |  |  | Subscriptions | Go to "Manage your Subscriptions" | Click on the link "Manage your Subscriptions" to go to the Subscription page | Not redirecting | Fail | 2023-02-28
78 |  |  |  | Go to "Having issues managing your subscriptions?" | Click on the link "Having issues managing your subscriptions?" to go to Get Subscription Access page | Not redirecting | Fail | 2023-02-28
79 |  |  | Get Subscription Access | Submit email id to register as a Subscription user | User to get email notification stating that they have access to the Subscriptions now | Unable to go to Manage your subscriptions | Fail | 2023-02-28
80 |  |  |  |  | Registered user should be able to go to the "Manage your Subscriptions" page | Unable to register | Fail | 2023-02-28
81 |  |  | Manage your Subscriptions | View Subscription list | User should be able to see all of their Past and Active Subscriptions in a list when thy land on "Manage your Subscription" page | Unable to register | Fail | 2023-02-28
82 |  |  |  | View individual Subscription | On clicking any Past or Active Subscription, user should be able to see the individual Subscription showing Product, Price, Frequency details and Selected Delivery Address as selected at the time of initiating the Subscription | Unable to register | Fail | 2023-02-28
83 |  |  |  | Edit Subscription - Quantity | User should have the ability to change the quantity of the Product in their Subscription | Unable to register | Fail | 2023-02-28
84 |  |  |  | Edit Subscription - Frequency | User should have the ability to change the Frequency of delivery in their Subscription | Unable to register | Fail | 2023-02-28
85 |  |  |  | Edit Subscription - Change Delivery Address | User should have the ability to change the Delivery Address in their Subscription | Unable to register | Fail | 2023-02-28
86 |  |  |  | Delete Subscription | User should have the ability to cancel the Active subscription | Unable to register | Fail | 2023-02-28
87 |  |  | View Default Address | Present Default Address should be visible in this section as the "Default Address" | User Default Address should be visible under "Default Address" heading on the Account page | Same as expected | Pass | 2023-02-28
88 |  |  |  | Check View Address link | After click on "View Addresses" link user should redirect to My addresses page. | Not available | Fail | 2023-02-28
89 |  |  | Manage Address | Go to My Account | After click on "My Account" link user should see all user submitted details. | Same as expected | Pass | 2023-02-28
90 |  |  |  | View Address | User should be able to view all previously entered address under the "Addresses" section of the page | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
91 |  |  |  |  | Under the "Addresses" section of the page, there should be one address marked as "default Address" | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
92 |  |  |  |  | Under each on the listed address there should be a link to "Edit" and "Delete" the address | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
93 |  |  |  | Add New Address | All address fields should accept alphanumeric and special character. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
94 |  |  |  |  | User should be able click "Country/region" drop down and select "United States" | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
95 |  |  |  |  | "First name" field should accept alphanumeric and special character. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
96 |  |  |  |  | "Last name" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
97 |  |  |  |  | "Company" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
98 |  |  |  |  | "Address" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
99 |  |  |  |  | "Apartment, suite, etc." field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
100 |  |  |  |  | "City" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
101 |  |  |  |  | "State" drop down should be work all state list should be visible in the drop down and user should be able to select specific state. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
102 |  |  |  |  | "ZIP code" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
103 |  |  |  |  | "Phone" field should accept only numeric values. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
104 |  |  |  |  | "Phone" field should not accept character and special character values it show error message "Please match the requested format" | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
105 |  |  |  | Set Default Address | User should be able Check and unchecked "Set default" checkbox | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
106 |  |  |  |  | After click on "Add Address" button Address should be add with all the provided details. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
107 |  |  |  | Edit Address | After click on Edit link user should be redirect to "Edit address" page. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
108 |  |  |  |  | User should be able click "Country/region" drop down and select "United States" | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
109 |  |  |  |  | "First name" field should accept alphanumeric and special character. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
110 |  |  |  |  | "Last name" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
111 |  |  |  |  | "Company" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
112 |  |  |  |  | "Address" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
113 |  |  |  |  | "Apartment, suite, etc." field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
114 |  |  |  |  | "City" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
115 |  |  |  |  | "State" drop down should be work all state list should be visible in the drop down and user should be able to select specific state. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
116 |  |  |  |  | "ZIP code" field should accept alphanumeric and special character . | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
117 |  |  |  |  | "Phone" field should accept only numeric values. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
118 |  |  |  |  | "Phone" field should not accept character and special character values it show error message "Please match the requested format" | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
119 |  |  |  |  | User should be able Check and unchecked "Set default" checkbox | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
120 |  |  |  |  | After click on "Update Address" button edited address field's should be updated. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
121 |  |  |  |  | After click on "Cancel" link user should be back to "Add New Address "page. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
122 |  |  |  | Delete Address | User should be able to delete existing address. | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
123 |  |  |  |  | User should be able to delete all of their listed address | Option unavailable. | Fail | 2023-02-28 | There is option of manage address, however, even that is not working
124 |  |  | Order History | Order history (for Single time buy and Subscription) should be visible on "My Account" page. | User should be able to see "Order History". | Orders not placed | Fail | 2023-02-28 | Need to check after order is placed
125 |  |  |  | User should be able to see the individual Order Details | On click on the individual Order, user should be shown the Order Details, which should contain information regarding Product, Price, Qty, Amount Paid, Date of Order and Order Status |  |  | 2023-02-28 | Need to check after order is placed
126 |  |  |  | If user haven't placed any order it should show a standard message | User should see "You haven't placed any orders yet." | Same as expected | Pass | 2023-02-28
127 |  |  | Request for Replacement Order | From the individual Order Details page, user should be able to order for a Replacement as per the defined terms | Click on "TO BE FILLED" to order the replacement Product | Orders not placed | Fail | 2023-02-28 | Need to check after order is placed
128 | Product | Product Scenario | Check Product Page all elements | Product image zoom in and zoom out and scroll left and right side should work fine | Product images user should able to see with zoom and scroll left and right side. | Function not available | Fail | 2023-02-28
129 |  |  |  | Product name should be visible as per brand guideline colour and font. | User should see selected product name. | Same as expected | Pass | 2023-02-28
130 |  |  |  | User Rating stars should be visible | User should see product rating. | Rating Zero. Rating says- Be the first to review | Fail | 2023-02-28 | Can be checked if rating is availble
131 |  |  |  | Total Number of review's written should be visible as a number next to the star ratings | User should see number of total review's written for the product | Rating Zero. Rating says- Be the first to review | Fail | 2023-02-28 | Can be checked if rating is availble
132 |  |  |  | After click on "star rating" or "reviews" link user should go to "Customer Reviews" page. | User should redirect to "Customer Reviews" page. | Rating Zero. Rating says- Be the first to review | Fail | 2023-02-28 | Can be checked if rating is availble
133 |  |  |  | Product price(s) should be visible in dollar | User should be able to see product price in dollar. | Same as expected | Pass | 2023-02-28
134 |  |  |  | "One Time Purchase" check box should be available .if One Time plan is activated for the Product | User should be able to check "One Time Purchase" | Same as expected | Pass | 2023-02-28
135 |  |  |  | User should be able to check only one check box at one time . | User should able to check only one box at one time either "Subscribe to save" or "one time purchase checkbox". | Same as expected | Pass | 2023-02-28
136 |  |  |  | "Subscribe to Save" check box should be available if Subscription plan is activated for the Product | User should be able to check ""Subscribe to Save" | Same as expected | Pass | 2023-02-28
137 |  |  |  | After checking "Subscribe to Save" checkbox price will be change to a discounted price | User should be able to see price difference after checked "Subscribe to Save" checkbox. | Function not available | Fail | 2023-02-28 | Can be tested after subscrib and save is added
138 |  |  |  | After cheking "Subscribe to Save" check box "Delivery every" drop down should be visible | User should be able to select specific "Deliver Every" frequency. | Same as expected | Pass | 2023-02-28
139 |  |  |  | Days mentioned in the delivery frequency dropdown for a subscription, should be as per what is mentioned in Recharge for the product with a recommended option | Delivery frequency and Days recommended should match with Recharge values | Same as expected | Pass | 2023-02-28
140 |  |  |  | After clicking on "Subscribe to Save" - "Save more on your subscription order with your Sight Matters coupon code." this tag line should be visible as per brand guideline colour and font. | User should be able to see "Save more on your subscription order with your Sight Matters coupon code." | Function not available | Fail | 2023-02-28
141 |  |  |  | Check "Subscription Details" link should available | User should be able to click on "Subscription Details" link. | Function available | Fail | 2023-02-28 | "Subscription Details" button not available.
142 |  |  |  | After clicking on "Subscription Details" link new pop up should come with a tagline "Products are automatically delivered on the schedule you choose" and "Learn More" link. | User should be able to click on "Learn More" link. | Button not available | Fail | 2023-02-28
143 |  |  |  | After clicking on "Learn More" link user should redirect to "Customer Care" page. | User should redirect to "Customer Care" page and see all details. | Customer is redirected to Subscriptions FAQ page | Fail | 2023-02-28
144 |  |  | Product Quantity Check | Product quantity select (+) and (-) button should be available and working | User should be able to add and remove product quantity before adding in the cart. | Same as expected | Pass | 2023-02-28
145 |  |  |  | By clicking on (+) button, value of Qty should increment by 1 | After click on (+) button product quantity should increased by 1. | Same as expected | Pass | 2023-02-28
146 |  |  |  | By clicking on (-) button, value of Qty should decrement by 1 | After click on (-) button product quantity should decreased by 1. | Same as expected | Pass | 2023-02-28
147 |  |  |  | Value of Qty should not go above 99 | User should not able to add product quantity more than 99 | Same as expected | Pass | 2023-02-28
148 |  |  |  | Value of Qty should not go below 0 | User should not able to select product quantity less than 1 | Same as expected | Pass | 2023-02-28
149 |  |  |  | Check "Add to Cart" button | Add to cart button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-02-28
150 |  |  |  | After click on " Add to Cart" button "Added to cart" this tagline and "View cart and check out." link come on top of the page with brand guideline colour. | User should see top of the page new tag line after click on "Add to Cart" button. | Same as expected | Pass | 2023-02-28
151 |  |  | Product Inventory Check | Value of Qty should not go above the available inventory quantity for the product | User should not able to add quantity more than available inventory quantity. | Same as expected | Pass | 2023-02-28
152 |  |  |  | If there is no inventory for the Product, the "Add to Cart" button label should get changed to "Temporarily Unavailable" | If product in not available it should show "Temporarily Unavailable". | It shows as add to cart and redirects to empty cart | Fail | 2023-02-28
153 |  |  | Product Marketing Information Section | Product Marketing section should be displayed if Marketing banner is provided by the Products/Marketing team | User should be able to see product marketing banner if product team provided. | Same as expected | Pass | 2023-02-28
154 |  |  |  | Product Marketing section should not be displayed if Marketing banner is not provided by the Products/Marketing team | User should not be able to see product marketing banner if product team not provided. | Same as expected | Pass | 2023-02-28
155 |  |  |  | Disclaimer available at the bottom of the Product Marketing Section | Disclaimer "*These statements have not been evaluated by the Food and Drug Administration. These products are not intended to diagnose, treat, cure or prevent any disease." available at the below of the Ingredient matter | Not available | Fail | 2023-02-28
156 |  |  | Shop Our Other Products | "Shop our other product" should be visible on all product pages | User should be able to see other products. | Same as expected | Pass | 2023-02-28
157 |  |  |  | User should see brand other product image, product link, product one time purchase price and subscription price. | User should see brand other product details. | Only Biotrue products are visible | Fail | 2023-02-28
158 |  |  |  | After click on individual product image user should see new pop up with product detail's, product images. | User should see product detail's. | Redirects to new page with product on which customer clicked | Fail | 2023-02-28 | Should show pop up box with product summary
159 |  |  | Check Customer review (submission only) | "Customer Reviews" header should be visible as per brand guideline colour and font. | User should see "Customer Reviews" header. | Same as expected | Pass | 2023-02-28
160 |  |  |  | Check Disclaimer | User should see disclaimer. | Same as expected | Pass | 2023-02-28
161 |  |  |  | After click on "Please review the Full Product Reviews Disclaimer" all disclaimer should be visible. | User should be able to see all disclaimer. | Same as expected | Pass | 2023-02-28
162 |  |  |  | "Star" rating should be visible with mentioned "Based on quantity reviews" | User should see product rating. | Zero reviews | Fail | 2023-02-28 | Can be checked after 1 or 2 reviews
163 |  |  |  | After click on "write a review" link user should be able to see "Write a review" page | User should be able to see "Write a review" page. | Same as expected | Pass | 2023-02-28
164 |  |  |  | Check "Name" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Name" field. | Same as expected | Pass | 2023-02-28
165 |  |  |  | Check blank "Name" field should not accept. | User can't submit a review with blank "Name" | Same as expected | Pass | 2023-02-28
166 |  |  |  | Check "Email" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Email" field. | Same as expected | Pass | 2023-02-28
167 |  |  |  | Check blank "Email" field should not accept. | User can't submit a review with blank "Email" | Same as expected | Pass | 2023-02-28
168 |  |  |  | "Email" field accept only email | "Email" field should not accept without "@" | Same as expected | Pass | 2023-02-28
169 |  |  |  | Check "Rating" | User should be able to select "Star" rating | Stars rating unavailable | Fail | 2023-02-28
170 |  |  |  | Check blank "Rating" field should not accept. | User can't submit a review with blank "Rating" | Same as expected | Pass | 2023-02-28
171 |  |  |  | Check "Review Title" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Review Title" field. | Same as expected | Pass | 2023-02-28
172 |  |  |  | Check blank "Review Title" field should not accept. | User can't submit a review with blank "Review Title" | Same as expected | Pass | 2023-02-28
173 |  |  |  | Check "Body of Review (1500)" field should accept alphanumeric and special character | User should enter alphanumeric and special character in the "Body of Review (1500)" field. | Same as expected | Pass | 2023-02-28
174 |  |  |  | Check blank "Body of Review (1500)" field should not accept. | User can't submit a review with blank "Body of Review (1500)" | Accepts more than 1500 characters | Fail | 2023-02-28
175 |  |  |  | Check "Body of Review (1500)" field should not accept more 1500 characters. | User should not be able to enter more than 1500 character. | Accepts more than 1500 characters | Fail | 2023-02-28
176 |  |  |  | Check "Body of Review (1500)" accept minimum '3' character | User need to be enter minimum '3' character "Body of Review (1500)" | Accepts less than 3 characters | Fail | 2023-02-28
177 |  |  |  | Write a review field's should not accept blank it should show error message. | It should show error message "Not all the fields have been filled out correctly!" | Same as expected | Pass | 2023-02-28
178 |  |  |  | Check "Submit Review" button should be work | Submit review button should be visible with colour as per brand guidelines. | Submit button as per brand | Fail | 2023-02-28 | Button not working
179 |  |  |  | After click on "Submit Review" button customer should be able to submit a customer review | After entered all Customer review field's user should be able to submit his review clicking on "Submit Review" button. | Review is not submitted | Fail | 2023-02-28
180 |  |  |  | After successfully submit a review user should see "Thank you for submitting a review!" line. | User should see "Thank you for submitting a review!" line. | Review is not submitted | Fail | 2023-02-28
181 |  |  |  | Other user's review should be visible | Customer should be able to read other customer review's. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
182 |  |  |  | Other user submitted rating star should be visible. | User should be able see "Star" rating. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
183 |  |  |  | Other user review header should be visible with colour and font should be as per brand guideline. | User should be able to read review header | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
184 |  |  |  | Review submitted user name and review published date should be visible. | User should be able to read review submitted customer name and published date. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
185 |  |  |  | Review description should be visible. | User should be read review description. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
186 |  |  |  | Check "Report as Inappropriate" link should be work | After click on "Report as Inappropriate" new pop-up should come its should ask "Are you sure you want to report this review as inappropriate?" with "Ok" and "Cancel" button. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
187 |  |  |  | Anyone can mark an already published review as "Report as Inappropriate" | Customer should be able to mark review as "Report as Inappropriate". | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
188 |  |  |  | Any review that is marked as "Inappropriate", should generate an alert at the backend for moderation | After customer submit "Report as Inappropriate" review it should be generate an alert at the backend for moderation. | Zero reviews | Fail | 2023-02-28 | Can be chaecked after few reviews submitted
189 |  | Check Single buy | Check "One Time Purchase" Buy | Check "One Time Purchase" checkbox | User should be able to check "One Time Purchase" checkbox. | Same as expected | Pass | 2023-02-28
190 |  |  |  | After click on "Add to Cart" button "My Cart" window should come on right side. | User should be able to see "My Cart" page details after click on "Add to Cart" button. | Same as expected | Pass | 2023-02-28
191 |  |  | Check "My Cart" drawer | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass | 2023-02-28
192 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Same as expected | Pass | 2023-02-28
193 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-02-28
194 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-02-28
195 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via Recharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via Recharge") | Same as expected | Pass | 2023-02-28
196 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-02-28
197 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-02-28
198 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Same as expected | Pass | 2023-02-28
199 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity and Subtotal | User should see all added products in the cart with details. | Same as expected | Pass | 2023-02-28
200 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass | 2023-02-28
201 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Same as expected | Pass | 2023-02-28
202 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-02-28
203 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | Button not available | Fail | 2023-02-28
204 |  |  |  | Product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Same as expected | Pass | 2023-02-28
205 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-02-28
206 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping, taxes, and discounts codes are calculated at checkout." | User should see tagline "Shipping, taxes, and discounts codes are calculated at checkout." | Same as expected | Pass | 2023-02-28
207 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass | 2023-02-28
208 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass | 2023-02-28
209 |  |  |  | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass | 2023-02-28
210 |  |  |  | After click on "Checkout" button user should redirect to "Contact information & Shipping address" page | User should redirect to "Contact & Shipping address" page | Same as expected | Pass | 2023-02-28
211 |  |  | Contact information | Check "Contact information" details | User should see his registered name and email | Same as expected | Pass | 2023-02-28
212 |  |  |  | Check "Log out" link | After click on "Log out" link user account should log out | Same as expected | Pass | 2023-02-28
213 |  |  |  | Check box | User should be able to check on " Yes, I would like to receive promotional communications from Bausch + Lomb." checkbox. | Check box not available | Fail | 2023-02-28
214 |  |  |  | Below the check box user should see disclaimer | By submitting your information you confirm you have read and agree with the terms of our Privacy Policy and Legal Notice . | Check box not available | Fail | 2023-02-28
215 |  |  |  | The link to privacy Policy should work fine | User should able to redirect to privacy policy page. | Functionality not available | Fail | 2023-02-28
216 |  |  |  | The link to Legal Notice should work fine | User should able to redirect legal notice page. | Functionality not available | Fail | 2023-02-28
217 |  |  | Order Summary | Selected product should be the same as selected by customer while making the order | Order list should be comparable to what was present in the respective Cart (use Cart ID) | Same as expected | Pass | 2023-02-28
218 |  |  |  | Product image, product name and product price should be visible. | User should see product details. | Same as expected | Pass | 2023-02-28
219 |  |  |  | Check Discount code | User should be able to enter discount code in the field. | Discount field unavailable | Fail | 2023-02-28
220 |  |  |  | After enter "Discount - code " click on "Apply" button. | After click on "Apply" button "Discount - code " should applied. | Discount field unavailable | Fail | 2023-02-28
221 |  |  |  | User should see Subtotal, Shipping, Estimated taxes and Total . | User should be able to see product price calculated values. | Discount field unavailable | Fail | 2023-02-28
222 |  |  |  | Check "Estimated taxes" | Estimated taxes should be calculated 7.5% of the product price. | Taxes not calculated | Fail | 2023-02-28
223 |  |  |  | Check "Total" | "Total" should be addition of Subtotal, Shipping and Estimated taxes | Shipping is calculated and added | Fail | 2023-02-28 | Taxes not added
224 |  |  | Shipping Address | Check "Shipping Address" field's. | User should see his already saved address on "Shipping Address" field's. | drop down unavailable | Fail | 2023-02-28
225 |  |  |  | Check "Saved Addresses" drop down. | User should see all saved address list in the drop down and able to select any one address in list. | drop down unavailable | Fail | 2023-02-28
226 |  |  |  | Check "Country/region" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country/region" drop down. | Same as expected | Pass | 2023-02-28
227 |  |  |  | Check "First name" field | User should see saved his "First name" and able to edit. | Same as expected | Pass | 2023-02-28
228 |  |  |  | Check "Last name" field | User should see saved his "Last name" and able to edit. | Same as expected | Pass | 2023-02-28
229 |  |  |  | Check "Address" field | User should see saved his "Address" and able to edit. | Same as expected | Pass | 2023-02-28
230 |  |  |  | Check "Apt, suite, etc." field | User should see saved his "Apt, suite, etc." and able to edit. | Same as expected | Pass | 2023-02-28
231 |  |  |  | Check "City" field | User should see saved his "City" and able to edit. | Same as expected | Pass | 2023-02-28
232 |  |  |  | Check "State" field | User should see selected his "Last name" and able to select another state in the drop down.. | User can click on "State" to select another state from drop down | Fail | 2023-02-28 | Test Case description incorrect
233 |  |  |  | Check "Zip code" field | User should see saved his "Zip code" and able to edit. | Same as expected | Pass | 2023-02-28
234 |  |  |  | Check "Return to Cart" link | After click on "Return to cart" link user should redirect "Shopping Cart" page. | Functionality not available | Fail | 2023-02-28
235 |  |  |  | Check "Continue" button | Check "Continue" button should be work with colour as per brand guidelines. | Same as expected | Pass | 2023-02-28
236 |  |  | Payment page | After click on "Continue" button user should redirect "Payment" page. | User should redirect to another page. | Same as expected | Pass | 2023-02-28
237 |  |  |  | Check "Contact" | Email_id should be visible and after click on "change" link user should redirect back to shipping page | Same as expected | Pass | 2023-02-28
238 |  |  |  | Check "Ship to" | Shipping details should be visible and after click on "change" link user should redirect back to shipping page | Same as expected | Pass | 2023-02-28
239 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Free standard shipping unavailable | Fail | 2023-02-28
240 |  |  |  | Check "Return to information" link | After click on "Return to information" user should redirect to shipping page. | Same as expected | Pass | 2023-02-28
241 |  |  |  | Check "Continue to payment" button | Check "Continue to payment" button should be work with colour as per brand guidelines. | Same as expected | Pass | 2023-02-28
242 |  |  |  |  | After click on "Continue to payment" button user should redirect "Payment" page. | Same as expected | Pass | 2023-02-28
243 |  |  |  | Check "Method" | It should show "Free Standard Shipping · Free" | Free standard shipping unavailable | Fail | 2023-02-28 | Standard and economy options available
244 |  |  |  | Check disclaimer | Payment- "All transactions are secure and encrypted." | Same as expected | Pass | 2023-02-28
245 |  |  |  | Check "Credit Card" field's. | User should see card logo. | Same as expected | Pass | 2023-02-28
246 |  |  |  | Check "Card number" field should accept only numeric values | User should be able to enter only numeric values in "Card number" field. | Same as expected | Pass | 2023-02-28
247 |  |  |  | Check "Card number" field should not accept character values. | User should not able to enter character values in "Card number" field. | Same as expected | Pass | 2023-02-28
248 |  |  |  | Check "Card number" field length should accept only 16 numeric values | User should be able to enter "Card number" length accept only 16 numeric values | Accepts more than 16 digits | Fail | 2023-02-28
249 |  |  |  | Blank "Card number" field should not accept it should show error massage (Your card number is incomplete.) | "Card number" field should not accept blank | Same as expected | Pass | 2023-02-28
250 |  |  |  | Check "Name on card "should accept character and numeric values | "Name on card" field should accept character and numeric values. | Same as expected | Pass | 2023-02-28
251 |  |  |  | Check blank "Name on card " should not accept. | User should see error message "Enter your name exactly as it’s written on your card" after providing blank details. | Same as expected | Pass | 2023-02-28
252 |  |  |  | Check "Expiration date" field should accept only numeric values | User should be able to enter only numeric values in "Expiration date "field. | Same as expected | Pass | 2023-03-01
253 |  |  |  | Check "Expiration" field should not accept character values. | User should not able to enter character values in "Expiration date "field. | Same as expected | Pass | 2023-03-01
254 |  |  |  | Check "Expiration date" field length should accept only 6 numeric values | User should be able to enter "Expiration date" field length accept only 6 numeric values | Accepts in format MM/YY | Fail | 2023-03-01
255 |  |  |  | Check "Expiration date" field should accept MM/YYYY format | User should be able to enter date in "MM/YYYY" format | Accepts in format MM/YY | Fail | 2023-03-01
256 |  |  |  | Blank "Expiration date" field should not accept | "Expiration date" field should not accept blank it show error message "Enter a valid card expiry date" | Same as expected | Pass | 2023-03-01
257 |  |  |  | Check "Security Code" field should accept only numeric values | User should be able to enter only numeric values in "Security Code" field. | Same as expected | Pass | 2023-03-01
258 |  |  |  | Check "Security Code" field should not accept character values. | User should not able to enter character values in "Security Code" field. | Same as expected | Pass | 2023-03-01
259 |  |  |  | Check "Security Code" field length should accept only 4 numeric values | User should be able to enter "Security Code" field length accept only 4 numeric values | Same as expected | Pass | 2023-03-01
260 |  |  |  | Blank "Security Code" field should not accept | "Security Code" field should not accept blank show error message "Enter the CVV or security code on your card" | Same as expected | Pass | 2023-03-01
261 |  |  | Billing Address | User should see header | Select the address that matches your card or payment method. | Same as expected | Pass | 2023-03-01
262 |  |  |  | Check "Same as shipping address" checkbox | User should be able check on checkbox | Same as expected | Pass | 2023-03-01
263 |  |  |  | Check "Use a different billing address" checkbox | User should be able check on checkbox | Same as expected | Pass | 2023-03-01
264 |  |  |  | User should select only one check box. | User should be able check either "Same as shipping address" or "Use a different billing address" checkbox only one check box at one time. | Same as expected | Pass | 2023-03-01
265 |  |  |  | Check "Use a different billing address" field's. | User should see all saved address field. | Same as expected | Pass | 2023-03-01
266 |  |  |  | Below the check box user should see disclaimer | By submitting your information you confirm you have read and agree with the terms of our Privacy Policy and Legal Notice . | Same as expected | Pass | 2023-03-01
267 |  |  |  | Check "Return to shipping" link | After click on "Return to shipping" user should redirect on shipping page. | Same as expected | Pass | 2023-03-01
268 |  |  |  | Check "Pay now" button | Colour and font should be as per brand guidelines. | Same as expected | Pass | 2023-03-01
269 |  |  |  | After click on "Pay now" button payment should successfully done | User should see placed order details | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
270 |  |  |  | User should received email notification on his register email. | User should received order details on his email. | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
271 |  |  |  |  | User should see Shipping Address, Billing Address | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
272 |  |  |  |  | User should see product item, price, quantity and total. | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
273 |  |  |  | Check "Subtotal" | User should see product price | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
274 |  |  |  | Check "Shipping (Free Standard Shipping)" | User should see shipping charges if free it should show 0 | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
275 |  |  |  | Check "Tax (MN COUNTY TAX 0.15%)" | Tax should be calculated 0.15% of the product price | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
276 |  |  |  | Check "Tax (MN STATE TAX 6.875%)" | Tax should be calculated 6.875 % of the product price | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
277 |  |  |  | Check "Tax (MN SPECIAL TAX 0.5%)" | Tax should be calculated 0.5% of the product price | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
278 |  |  |  | Check "Total" | User should see final amount addition of subtotal + shipping + all taxes | Store can't accept orders at this moment | Fail | 2023-03-01 | Can be tested once we can place order
279 |  | Check subscription buy | Check "Subscribe to Save" Buy | Check "Subscribe to Save" checkbox | User should be able to check "Subscribe to Save" checkbox. | Same as expected | Pass | 2023-03-01
280 |  |  |  | "Subscribe to Save" check box should be available if Subscription plan is activated for the Product | User should be able to check "Subscribe to Save" | Functionality not available | Fail | 2023-03-01
281 |  |  |  | After checking "Subscribe to Save" checkbox price will be change to a discounted price | User should be able to see price difference after checked "Subscribe to Save" checkbox. | Same as expected | Pass | 2023-03-01
282 |  |  |  | After cheking "Subscribe to Save" check box "Delivery every" drop down should be visible | User should be able to select specific "Deliver Every" frequency. | Same as expected | Pass | 2023-03-01
283 |  |  |  | Days mentioned in the delivery frequency dropdown for a subscription, should be as per what is mentioned in Recharge for the product with a recommended option | Delivery frequency and Days recommended should match with Recharge values | Same as expected | Pass | 2023-03-01
284 |  |  |  | After clicking on "Subscribe to Save" - "Save more on your subscription order with your Sight Matters coupon code." this tag line should be visible as per brand guideline colour and font. | User should be able to see "Save more on your subscription order with your Sight Matters coupon code." | Same as expected | Pass | 2023-03-01
285 |  |  |  | After click on "Add to Cart" button "My Cart" window should come on right side. | User should be able to see "My Cart" page details after click on "Add to Cart" button. | Same as expected | Pass | 2023-03-01
286 |  |  | Check "My Cart" page | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass | 2023-03-01
287 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Same as expected | Pass | 2023-03-01
288 |  |  |  | Check "Delivery Frequency" | User selected Delivery Frequency should be visible | Doesn't show delivery frequency | Fail | 2023-03-01
289 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-03-01
290 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-03-01
291 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via Recharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via Recharge") | Same as expected | Pass | 2023-03-01
292 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-03-01
293 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-03-01
294 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Same as expected | Pass | 2023-03-01
295 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity, delivery frequency | User should see all added products in the cart with details. | Same as expected | Pass | 2023-03-01
296 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass | 2023-03-01
297 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Same as expected | Pass | 2023-03-01
298 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-03-01
299 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | Functionality not available | Fail | 2023-03-01
300 |  |  |  | Below of the added product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Same as expected | Pass | 2023-03-01
301 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-03-01
302 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass | 2023-03-01
303 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping and taxes will be completed securely via Recharge" | User should see tagline ""Shipping and taxes will be completed securely via Recharge" | Same as expected | Pass | 2023-03-01
304 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass | 2023-03-01
305 |  |  | Checkout | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass | 2023-03-01
306 |  |  |  | After click on "Checkout" button user should redirect to "Customer & Shipping Information" page | User should redirect to "Customer & Shipping Information" page | Same as expected | Pass | 2023-03-01
307 |  |  | Customer & Shipping Information | Customer should be able to fill "Customer & Shipping Information" Email fields. | "Email" field should accept alphanumeric and special character. | Same as expected | Pass | 2023-03-01
308 |  |  |  | Check blank "Email" should not accept. | "Email" field should not accept blank it should show "Please enter a valid email address" | Same as expected | Pass | 2023-03-01
309 |  |  | Order Summary | All product list should be visible those are customer selected for particular order. | User should see product list. | Same as expected | Pass | 2023-03-01
310 |  |  |  | Individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass | 2023-03-01
311 |  |  |  | User should see Subtotal, Shipping, Taxes, Total and Payment Due. | User should be able to see product price calculated values. | Tax not visible | Fail | 2023-03-01
312 |  |  | Use Promo code | After click on "Have a discount code? Enter it here" user should able to enter promo-code. | User should able to enter promo-code. | Functionality not available | Fail | 2023-03-01
313 |  |  |  | After enter "Discount - code promo" click on "Ok" button. | After click on "Ok" button "Discount - code promo" should applied. | Functionality not available | Fail | 2023-03-01
314 |  |  |  | Check blank "Discount - code promo" should not accept. | "Ok" button should not work after providing blank "Discount - code promo" | Functionality not available | Fail | 2023-03-01
315 |  |  |  | Check if code is not valid it show error message "Unable to find a valid discount matching the code entered" | User should see error message after entered wrong code. | Functionality not available | Fail | 2023-03-01
316 |  |  | Shipping Address | Check "Shipping Address" all fields it should accept alphanumeric and special character | All fields should accept alphanumeric and special character. | Same as expected | Pass | 2023-03-01
317 |  |  |  | Check "First name" field should accept alphanumeric and special character | User should be able to enter his "First name" | Same as expected | Pass | 2023-03-01
318 |  |  |  | Check "Last name" field should accept alphanumeric and special character | User should be able to enter his "Last name" | Same as expected | Pass | 2023-03-01
319 |  |  |  | Check blank "Last name" should not accept it should show error message "Missing data for required field." | Blank "Last name" field should not accept. | Same as expected | Pass | 2023-03-01
320 |  |  |  | Check "Company" field should accept alphanumeric and special character | User should be able to enter his "Company" | Same as expected | Pass | 2023-03-01
321 |  |  |  | Check "Address" field should accept alphanumeric and special character | User should be able to enter his "Address" | Same as expected | Pass | 2023-03-01
322 |  |  |  | Check blank "Address" should not accept it should show error message "Missing data for required field." | Blank "Address" field should not accept. | Same as expected | Pass | 2023-03-01
323 |  |  |  | Check "Apt, suite, etc." field should accept alphanumeric and special character | User should be able to enter his "Apt, suite, etc." | Same as expected | Pass | 2023-03-01
324 |  |  |  | Check "City" field should accept alphanumeric and special character | User should be able to enter his "City" | Same as expected | Pass | 2023-03-01
325 |  |  |  | Check blank "City" should not accept it should show error message "Shorter than minimum length 1." | Blank "City" field should not accept. | Same as expected | Pass | 2023-03-01
326 |  |  |  | "City" field minimum 1 character length should not accept less character. | "City" field length should be minimum 1 character . | Same as expected | Pass | 2023-03-01
327 |  |  |  | Check "Country" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country" drop down. | Same as expected | Pass | 2023-03-01
328 |  |  |  | Check "State" field | User should see all State list in "State" drop down. | Same as expected | Pass | 2023-03-01
329 |  |  |  | "Zip code" field should accept only numeric values. | Zip code field should accept only numeric values. | Same as expected | Pass | 2023-03-01
330 |  |  |  | "Zip code" field should not accept alphabetical and special character. | "Zip Code" should show "Invalid data: The US zip code must be the standard 5 digit number" when we enter alphabetical and special character. | Same as expected | Pass | 2023-03-01
331 |  |  |  | Blank "Zip code" field should not accept it show error message "Missing data for required field." | Blank "Zip Code" should not accept. | Same as expected | Pass | 2023-03-01
332 |  |  |  | Check "Phone" field should accept alphanumeric | User should be able to enter his "Phone" | Same as expected | Pass | 2023-03-01
333 |  |  |  | Check "Continue" button should be work with colour as per brand guidelines. | After click on "Continue" button user should redirect "Billing And Payment" page. | Same as expected | Pass | 2023-03-01
334 |  |  |  | After click on "Continue" button user should redirect to "Billing And Payment" page. | User should redirect "Billing And Payment" page. | Same as expected | Pass | 2023-03-01
335 |  |  | Payment page | "Customer & Shipping Information" visible on top of left side of the page. | User should be able to see "Customer & Shipping Information" details. | Same as expected | Pass | 2023-03-01
336 |  |  |  | Check "Edit" link for "Customer & Shipping Information" | User should be able edit his "Customer & Shipping Information" with click on "Edit" link. | Functionality not available | Fail | 2023-03-01
337 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Free standard shipping unavailable | Fail | 2023-03-01 | Standard and Economy Option availabke
338 |  |  | Billing And Payment | All card logo should be placed | User should see card logo. | Same as expected | Pass | 2023-03-01
339 |  |  |  | Check "Name on card "should accept character and numeric values | "Name on card" field should accept character and numeric values. | Same as expected | Pass | 2023-03-01
340 |  |  |  | Check "Card number" field should accept only numeric values | User should be able to enter only numeric values in "Card number" field. | Same as expected | Pass | 2023-03-01
341 |  |  |  | Check "Card number" field should not accept character values. | User should not able to enter character values in "Card number" field. | Same as expected | Pass | 2023-03-01
342 |  |  |  | Check "Card number" field length should accept only 16 digit numeric values | User should be able to enter "Card number" length accept only 16 digit numeric values | Accepts more tha 16 digit | Fail | 2023-03-01
343 |  |  |  | Blank "Card number" field should not accept it should show error massage (Your card number is incomplete.) | "Card number" field should not accept blank | Same as expected | Pass | 2023-03-01
344 |  |  |  | Check "Expiration" field should accept only numeric values | User should be able to enter only numeric values in "Expiration "field. | Same as expected | Pass | 2023-03-01
345 |  |  |  | Check "Expiration" field should not accept character values. | User should not able to enter character values in "Expiration "field. | Same as expected | Pass | 2023-03-01
346 |  |  |  | Check "Expiration" field length should accept only 4 numeric values | User should be able to enter Expiration" field length accept only 4 numeric values | Same as expected | Pass | 2023-03-01
347 |  |  |  | Blank "Expiration" field should not accept | "Expiration" field should not accept blank | Same as expected | Pass | 2023-03-01
348 |  |  |  | Check "CVV" field should accept only numeric values | User should be able to enter only numeric values in "CVV" field. | Same as expected | Pass | 2023-03-01
349 |  |  |  | Check "CVV" field should not accept character values. | User should not able to enter character values in "CVV" field. | Same as expected | Pass | 2023-03-01
350 |  |  |  | Check "CVV" field length should accept only 4 numeric values | User should be able to enter "CVV" field length accept only 4 numeric values | Same as expected | Pass | 2023-03-01
351 |  |  |  | Blank "CVV" field should not accept | "CVV" field should not accept blank | Same as expected | Pass | 2023-03-01
352 |  |  | Billing Address | Check previously added billing address should be visible and user should be able to check checkbox . | User should see previously added billing address and user should be able to check checkbox . | Same as expected | Pass | 2023-03-01
353 |  |  |  | User should check checkbox either previously added "billing address" or "Use a different billing address" check box. | User should check only one check box at one time. | Same as expected | Pass | 2023-03-01
354 |  |  |  | Check "Use a different billing address" check box. | After checked check box of "Use a different billing address" should open new page. | Same as expected | Pass | 2023-03-01
355 |  |  |  | Check "Billing Address" all fields it should accept alphanumeric and special character | All fields should accept alphanumeric and special character. | Same as expected | Pass | 2023-03-01
356 |  |  |  | Check "First name" field should accept alphanumeric and special character | User should be able to enter his "First name" | Same as expected | Pass | 2023-03-01
357 |  |  |  | Check "Last name" field should accept alphanumeric and special character | User should be able to enter his "Last name" | Same as expected | Pass | 2023-03-01
358 |  |  |  | Check blank "Last name" should not accept it should show error message "Missing data for required field." | Blank "Last name" field should not accept. | Same as expected | Pass | 2023-03-01
359 |  |  |  | Check "Company" field should accept alphanumeric and special character | User should be able to enter his "Company" | Same as expected | Pass | 2023-03-01
360 |  |  |  | Check "Address" field should accept alphanumeric and special character | User should be able to enter his "Address" | Same as expected | Pass | 2023-03-01
361 |  |  |  | Check blank "Address" should not accept it should show error message "Missing data for required field." | Blank "Address" field should not accept. | Same as expected | Pass | 2023-03-01
362 |  |  |  | Check "Apt, suite, etc." field should accept alphanumeric and special character | User should be able to enter his "Apt, suite, etc." | Same as expected | Pass | 2023-03-01
363 |  |  |  | Check "City" field should accept alphanumeric and special character | User should be able to enter his "City" | Same as expected | Pass | 2023-03-01
364 |  |  |  | Check blank "City" should not accept it should show error message "Shorter than minimum length 1." | Blank "City" field should not accept. | Same as expected | Pass | 2023-03-01
365 |  |  |  | "City" field minimum 1 character length should not accept less character. | "City" field length should be minimum 1 character . | Same as expected | Pass | 2023-03-01
366 |  |  |  | Check "Country" drop down "United States" name should be visible in drop down. | "United States" should be visible in "Country" drop down. | Same as expected | Pass | 2023-03-01
367 |  |  |  | Check "State" field | User should see all State list in "State" drop down. | Same as expected | Pass | 2023-03-01
368 |  |  |  | "Zip code" field should accept only numeric values. | Zip code field should accept only numeric values. | Same as expected | Pass | 2023-03-01
369 |  |  |  | "Zip code" field should not accept alphabetical and special character. | "Zip Code" should show "Invalid data: The US zip code must be the standard 5 digit number" when we enter alphabetical and special character. | Same as expected | Pass | 2023-03-01
370 |  |  |  | Blank "Zip code" field should not accept it show error message "Missing data for required field." | Blank "Zip Code" should not accept. | Same as expected | Pass | 2023-03-01
371 |  |  |  | Check "Phone" field should accept alphanumeric | User should be able to enter his "Phone" | Same as expected | Pass | 2023-03-01
372 |  |  |  | Check check-box below of the billing address | User should be able to check our unchecked below billing address check-box "Yes, I would like to receive promotional communications from Bausch + Lomb." | Check box not available | Fail | 2023-03-01
373 |  |  |  | Check disclaimer | "By clicking "Place my order", you confirm that your subscription will automatically renew and your credit card will automatically be charged the subscription price according to the Order summary section of this page until you cancel your subscription. You also authorize PreserVision to charge the supplied payment method, or another payment method on file, for the subscription price on each renewal. You can cancel your subscription at any time." | Unable to proceed further from Pay | Fail | 2023-03-01
374 |  |  |  | Check "Place my order" button | User should be able to click "Place my order" button with colour as per brand guidelines. | Unable to proceed further from Pay | Fail | 2023-03-01
375 |  |  |  | After click on "Place my order" button order should placed successfully. | User order should placed successfully after click on "Place my order" button | Unable to proceed further from Pay | Fail | 2023-03-01
376 |  |  |  | Check email notification | After order placed user should received email notification on his email. | Unable to proceed further from Pay | Fail | 2023-03-01
377 |  | Check product both buy option | Check both "Subscribe to Save" and "One Time Purchase" buy | Select product in the cart one is "subscribe to save" and other is "One time purchase" |  | Same as expected | Pass | 2023-03-01
378 |  |  | Check "My Cart" page | Check all added product's should be available in the "My Cart "page. | User should be able to see all added product's in the cart with product name, product image, product price. | Same as expected | Pass | 2023-03-01
379 |  |  |  | Check "Remove" link | User should be able to remove added product's in the cart after click on "Remove" link | Same as expected | Pass | 2023-03-01
380 |  |  |  | Check "Delivery Frequency" | If user "Subscribe to Save" selected product below Delivery Frequency should be visible | Delivery frequency doesn't show up | Fail | 2023-03-01
381 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-03-01
382 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-03-01
383 |  |  |  | Below of the "Subtotal" tagline should be visible ("Free Standard Shipping, Checkout will be completed securely via ReCharge") | User should see tagline ( "Free Standard Shipping, Checkout will be completed securely via ReCharge") | No tagline available | Fail | 2023-03-01 | The line says "FREE STANDARD SHIPPING, TAXES CALCULATED AT CHECKOUT."
384 |  |  |  | Check "VIEW CART" button | "VIEW CART" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-03-01
385 |  |  |  | Check "CHECKOUT" button | "CHECKOUT" button should be visible with colour should be as per the brand guidelines. | Same as expected | Pass | 2023-03-01
386 |  |  | Check "Shopping Cart" page | After click on "VIEW CART" button user should redirect to "Shopping Cart" page | "VIEW CART" button should be work and user should see "Shopping Cart" page. | Same as expected | Pass | 2023-03-01
387 |  |  |  | User should be able to see all earlier added products list in the cart with price, quantity, delivery frequency | User should see all added products in the cart with details. | Same as expected | Pass | 2023-03-01
388 |  |  |  | Check each and every individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass | 2023-03-01
389 |  |  |  | Check subscribe to save product details | If product selected subscribe to save below "Delivery Frequency" should be visible. | Delivery frequency not visible | Fail | 2023-03-01
390 |  |  |  | Check individual product link | After click on individual product link user should redirect to particular page. | Same as expected | Pass | 2023-03-01
391 |  |  |  | User should be able to add and remove quantity of the product. | After click on (+) and (-) buttons product quantity should add or remove. | Same as expected | Pass | 2023-03-01
392 |  |  |  | Check "Cross" sign should be work | After click on "Cross" sign product should be remove from "Shopping Cart" page | "Cross" button unavailable | Fail | 2023-03-01
393 |  |  |  | Below of the added product below tagline should be visible "Proceed to Checkout to enter your Sight Matters coupon code" | User should be able to see tagline "Proceed to Checkout to enter your Sight Matters coupon code" | Same as expected | Pass | 2023-03-01
394 |  |  |  | All added product's "Subtotal" should be visible. | User should be able to see product's "Subtotal" | Same as expected | Pass | 2023-03-01
395 |  |  |  | User should be able to "write any special instruction for his shipment" in left side box in the shopping cart page. | User should write any special instruction at the time of checkout. | Same as expected | Pass | 2023-03-01
396 |  |  |  | Below of the product's "Subtotal" tagline should be visible "Shipping and taxes will be completed securely via Recharge" | User should see tagline ""Shipping and taxes will be completed securely via Recharge" | Line unavailable | Fail | 2023-03-01
397 |  |  |  | Check tagline | "Our carriers are currently experiencing some delays that are outside our control. As a result, your order might take a little longer than usual to get delivered. Thank you for your understanding and your patience." | Same as expected | Pass | 2023-03-01
398 |  |  |  | Check "Checkout" button | Checkout button should be visible and colour as per the brand guidelines. | Same as expected | Pass | 2023-03-01
399 |  |  |  | After click on "Checkout" button user should redirect to "Customer & Shipping Information" page | User should redirect to "Customer & Shipping Information" page | Same as expected | Pass | 2023-03-01
400 |  |  | Customer & Shipping Information | "Customer & Shipping Information" visible on top of left side of the page. | User should be able to see "Customer & Shipping Information" details. | The name not visibile | Fail | 2023-03-01
401 |  |  |  | Check "Edit" link for "Customer & Shipping Information" | User should be able edit his "Customer & Shipping Information" with click on "Edit" link. | Edit link unavailable | Fail | 2023-03-01 | Change option available
402 |  |  |  | Check Shipping checkbox - "Free Standard Shipping" | User should be able to see Shipping checkbox. | Free shipping unavailable | Fail | 2023-03-01 | Standard and economy option available
403 |  |  | Order Summary | All product list should be visible those are customer selected for particular order. | User should see product list. | Same as expected | Pass | 2023-03-01
404 |  |  |  | Individual product image, product name and product price should be visible. | User should see individual product details. | Same as expected | Pass | 2023-03-01
405 |  |  |  | User should see Subtotal, Shipping, Taxes, Total and Payment Due. | User should be able to see product price calculated values. | Tax not Calculated | Fail | 2023-03-01
406 |  |  |  | Check "taxes" | taxes should be calculated 7.5% of the product price. | Taxes not calculated | Fail | 2023-03-01
407 |  |  |  | Check "Total" | "Total" should be addition of Subtotal, Shipping and Estimated taxes | Same as expected | Pass | 2023-03-01
408 |  |  |  | Check "Payment Due" | "Payment Due" should be addition of Subtotal, Shipping and Estimated taxes | Wroks like normal chefck out. No payment due found | Fail | 2023-03-01
409 |  |  | Use Promo code | After click on "Have a discount code? Enter it here" user should able to enter promo-code. | User should able to enter promo-code. | Not visible | Fail | 2023-03-01
410 |  |  |  | After enter "Discount - code promo" click on "Ok" button. | After click on "Ok" button "Discount - code promo" should applied. | Not visible | Fail | 2023-03-01
411 |  |  |  | Check blank "Discount - code promo" should not accept. | "Ok" button should not work after providing blank "Discount - code promo" | Not visible | Fail | 2023-03-01
412 |  |  |  | Check if code is not valid it show error message "Unable to find a valid discount matching the code entered" | User should see error message after entered wrong code. | Not visible | Fail | 2023-03-01
413 |  |  | Billing And Payment | All card logo should be placed | User should see card logo. | Same as expected | Pass | 2023-03-01
414 |  |  |  | Check payment fields. | Check all credit card field's. | Same as expected | Pass | 2023-03-01
415 |  |  | Billing Address | Check all billing address fields. | User should be able to enter all details in billing field's. | Same as expected | Pass | 2023-03-01
416 |  |  |  | Check check-box below of the billing address | User should be able to check our unchecked below billing address check-box "Yes, I would like to receive promotional communications from Bausch + Lomb." | Not visible | Fail | 2023-03-01
417 |  |  |  | Check disclaimer | "By clicking "Place my order", you confirm that your subscription will automatically renew and your credit card will automatically be charged the subscription price according to the Order summary section of this page until you cancel your subscription. You also authorize PreserVision to charge the supplied payment method, or another payment method on file, for the subscription price on each renewal. You can cancel your subscription at any time." | Not visible | Fail | 2023-03-01
418 |  |  |  | Check "Place my order" button | User should be able to click "Place my order" button with colour as per brand guidelines. | Instead of "Place my Order" There is "Pay Now" | Fail | 2023-03-01
419 |  |  |  | After click on "Place my order" button order should placed successfully. | User order should placed successfully after click on "Place my order" button | Functionality not available | Fail | 2023-03-01
420 |  |  |  | Check email notification | After order placed user should received email notification on his email. | Store not ready for orders | Fail | 2023-03-01
421 | Checkout | Checkout Scenario | Sold-out | Check if product is not available it should show "Temporarily Unavailable" | If product is not available it should show "Temporarily Unavailable" with colour as per brand guidelines. | Doesn't show | Fail | 2023-03-01
422 |  |  | Abandoned Cart | User may have received abandoned cart emails notification on his registered email. | User should see abandoned cart notification email |  |  | 2023-03-01
423 |  |  | Request for Cancellation of Subscription | User should be able to cancel subscription. | After click on "Manage Your Subscriptions" button user should be able to cancel subscription. | Functionality not available | Fail | 2023-03-01
424 | Integration Scenarios | KH Integration Scenario | Authentication API | Check Authentication is occurred via Knipper | Authentication is done by via Knipper. | 200 Ok response with Token | Pass | 2023-03-01
425 |  |  |  | Check the Authentication API header ClientID, client secret, grant type and resource | Values should be accepted | 200 Ok response with Token | Pass | 2023-03-01
426 |  |  |  | Check Shopify token request to Knipper with all variable. | Request token should be send to Knipper | 200 Ok response with Token | Pass | 2023-03-01
427 |  |  |  | Check Knipper token response to Shopify with all variable.( access token, token type, expires in, extemporising, expires on, not before and resource) | Token response should be come in Shopify end with all field's. | 200 Ok response with Token | Pass | 2023-03-01
428 |  |  |  | Check Authentication response "200-ok " if success | If success response should be come "200-ok" | 200 Ok response with Token | Pass | 2023-03-01
429 |  |  | Order API | Check Authentication response "404 - Not Found " if failed | If failed response should be come "404 - Not Found" | For orders- 1009, 1011, 1019 | Pass | 2023-03-01 | If few fields are missing the this response comes
430 |  |  |  | Check Shopify order details request to Knipper with all variables. | Order details request should send to Knipper with all field's | 200 Ok response shows that Knipper accepts data with mentioned order details | Pass | 2023-03-01
431 |  |  |  | Check Knipper response with response code | Every time Knipper response should come in code either"200-ok" or "404- Not Found". | Same as expected | Pass | 2023-03-01
432 |  |  | Order Status API | Check order should send to Knipper this format Email, first name, last name, company, address, apartment, suite, city, country, state, zip code, phone, suffix, salutation, designation, attention to, Item code and quantity | Order format should match | Suffix, Salutation, designation and attention to missing | Fail | 2023-03-01 | Not mandatory
433 |  |  |  | Check Knipper order status details response to Shopify . | Order status response should be come at Shopify end. | Automation error | Fail | 2023-03-01 | Functionality not available. Knipper should send data either via email or POST to any of their specified endpoints
434 |  |  |  | Shopify will send the values to Knipper (one-time) that will be used for the Authentication API header (ClientID, client secret, grant type and resource) | Authentication values should be same those Shopify shared to Knipper | Automation error | Fail | 2023-03-01 | FulfillEO app doesn't have option for sending tokens
435 |  |  |  | Knipper to send request for a token using the above values | Shopify shared values should Knipper use for token request. | Automation error | Fail | 2023-03-01 | FulfillEO app doesn't have option for sending tokens
436 |  |  |  | Check Order Status change done by Knipper | Order status is done by via Knipper. | Automation error | Fail | 2023-03-01
437 |  |  |  | Check Knipper will send the Order Status details to Shopify after the above token is accepted with the following fields. ( Order: Status Description, Order Number: Request ID, Tracking Number: Tracking Number, Tracking Company: Courier Name) | Order status format should be match. | Fields match | Pass | 2023-03-01
438 | PG Integration Scenario | Payment Response | Contact information and Shipping address | Check order status should send emails notification on his registered email | Order status should come on registered email. | Email sent to customer | Pass | 2023-03-01
439 |  |  |  | Check all fields should accepts alphanumeric Email, first name, last name, company, address, apartment, suite, city, country, state, zip code, phone. | All fields should accept alphanumeric and special character. | Same as expected | Pass | 2023-03-01
440 |  |  |  | Check Payment, Billing address after providing correct all card details payment should be successful done. | After providing correct card details payment should be successfully done. | Same as expected | Pass | 2023-03-01
441 |  |  |  | Check after successfully payment done system should send emails notification on his registered email | Payment done notification should be send on customer email. | Same as expected | Pass | 2023-03-01
442 |  |  |  | Check after providing wrong card details systems should show error message (Your payment details couldn’t be verified. Check your card details and try again.) | Wrong card details should not accept. | Same as expected | Pass | 2023-03-01
443 | Replacement Order | Check Replacement Order | Check Order Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | There should be an older order reference in "Notes" for each Replacement Order
444 |  |  | Check Product Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | The replacement order should have a reference to the Product(s) that have been ordered before
445 |  |  | Customer Reference | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | The replacement order should be done for the Customer for whom there is an elaready existing paid order
446 |  |  | Check Amount | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Replacement Order amount should always be ZERO and does not pass through the payment gateway
447 |  |  | Check Address | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Replament order should have a Shipping address that can be similar to the existing Order or can also be different
448 |  |  | Check Tagging | Go to Orders, and filter by "Replacement" tag. Clcik on the concerned Order ID to check | Each replacement order should be tagged as "Replacement" under the field "Tags"
449 | Data Migration | Import Products | All Active Products | Check Product counts
450 |  |  |  | Check Product Information and Media
451 |  |  |  | Set Product Inventory
452 |  |  | All Draft Products | Check Product counts
453 |  |  |  | Check Product Information and Media
454 |  |  |  | Set Product Invetory
455 |  | Import Customers | All Customers | Check Customer Count
456 |  |  |  | Check Customer Information (randomly)
458 |  | Import Transactions | All Transactions | Check Transaction counts
459 |  |  |  | Check Transaction values (randomly and in aggregation)
460 |  | Import Orders (Single Buy) | All Single Buy Orders | Check Order counts
461 |  |  |  | Check Order Details (randomly)
462 |  | Import Orders (Subscriptions) | All Subscriptions | Check Order counts
463 |  |  |  | Check Order Details (randomly)
464 |  |  |  | Check Cusmtore Detals (randomly)
465 |  | Import Discount Codes | All Discount Codes | Check Discount Code count
466 |  |  |  | Check Active Discount Code settings (randomly)
467 |  |  |  | Check if Discounyt Code works
468 |  | Import Gift Cards | All Gift Cards | Check Gift Cards count
469 |  |  |  | Check an active Gift Card's settings (randomly)
470 |  |  |  | Check if an active Gift Card works (randomly)

## LoVs
Pass? | Status
Pass | Pass
Fail | Fail
Fixed
Deferred